## Page1_1
PLC Labor Hours Budget v. Actual
2019
Project L2 | GLC | Employee | January | February | March | April | May | June | July | August | September | October | November | December | YTD Actual Hours | Budget | Difference
901807.00 Next Gen Acoust Dorado | DMO-AUV Support
|  | Thomas, Hans (0436) | 0 | 10 | 8 | 0 | 70.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88.5 | 120 | 31.5
| DMO-AUV Support - Total |  | 0 | 10 | 8 | 0 | 70.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88.5 | 120 | 31.5
ENG-Associate Engineer
|  | Parker, Michael (0200) | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | -28
| ENG-Associate Engineer - Total |  | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | -28
ENG-Electrical Engineer
|  | Chaffey, Mark (0118) | 0 | 47 | 4 | 0 | 3 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 200 | 117
|  | Martin, Eric (0873) | 22 | 18.5 | 17 | 13.5 | 43 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 300 | 180
|  | McGill, Paul (0331) | 4 | 8 | 3 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 200 | 177
| ENG-Electrical Engineer - Total |  | 26 | 73.5 | 24 | 13.5 | 50 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 700 | 474
ENG-Electrical Tech
|  | Employee Not Specified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40
|  | Montgomery, Jim (0754) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -1
|  | Rosal, Jose (0591) | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | -3
| ENG-Electrical Tech - Total |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 40 | 36
ENG-Machinist
|  | Thompson, Ford (0534) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60
| ENG-Machinist - Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60
ENG-Mechanical Engineer
|  | Cazenave, Francois (0735) | 0 | 39 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 66 | 6
| ENG-Mechanical Engineer - Total |  | 0 | 39 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 66 | 6
ENG-Software Engineer-Embedded
|  | Henthorn, Richard (0414) | 0 | 0 | 0 | 18 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 50 | 28
|  | McEwen, Robert (0119) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16
| ENG-Software Engineer-Embedded - Total |  | 0 | 0 | 0 | 18 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 66 | 44
901807.00 Next Gen Acoust Dorado - Total |  |  | 26 | 122.5 | 36 | 35.5 | 169.5 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 428.5 | 1052 | 623.5
Report Total |  |  | 26 | 122.5 | 36 | 35.5 | 169.5 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 428.5 | 1052 | 623.5
Report Name: Labor Hours for PCO_Budget vs Actual |  |  | April: - 1 -; October: 2019-07-08
10:33