## Slide 1: AGENDA MBARI 4K ROV Camera housing build vs buy discussion Rev. B 10/22/19
October 23, 2019

## Slide 2: Agenda
Background
RFP and requirements review
Vendor proposals and detailed response matrix
In-house vs out-of-house decision matrix
Discussion points

## Slide 3: Background
902001 ROV 4K Camera project approved as 2020 project.
Project proposed and budgeted as an in-house design-and-build, although discussions with commercial vendors offered the possibility of a collaborative development.
Subsequent to project approval an RFP was sent to five commercial camera vendors with detailed specifications to see if a commercial vendor could provide a high quality housing at a reasonable cost.
MBARI would provide all of the camera and chassis components.
With vendor bids in hand, build in-house or contract out?

## Slide 4: Request for Proposals and Requirements
Formal request for proposals sent out Sept. 20, 2029:
“MBARI 4K ROV Camera System Request for Proposals
rev. B 20SEP19 Mark Chaffey. Included MBARI performing pressure test option.”
Referenced :
“MBARI 4K ROV Camera System Requirements
Doc. # 100221373
rev. C. 20SEP19 Mark Chaffey. Initial release.”

## Slide 5: Development Plan for Vendors
Vendor would provide optical design, optical dome port, relay optics, supporting structure and the pressure housing.
  Essentially the optical subsystem and the pressure housing.
MBARI will provide all else, camera, lens, control electronics, chassis, power supplies, connectors, cables, control box, etc.
  We can take the effort to reduce overall size by about 25-30mm in housing diameter.
  We receive a 40% discount from Sony and Fujinon.
  We have perfected the human interface/control box.
    Camera controls.
    Interface to shipboard reporting and data system.
Interface is the camera chassis to housing mounting arrangement.

## Slide 7
This column is if we ultimately purchase 3 units (no NRE split)
Higher NRE but lower unit 2 & 3 cost

## Slide 8: Pricing
Sulis Camera, SubC Imaging and Sidus Solutions provided fixed price bids.
Deep Sea Power & Light:
Q: Can you provide more detail on the housing cost estimate? How can we be assured that the estimate is close to the final cost? Is this possible? It is difficult to evaluate your proposal on a cost criteria if the final cost is not fixed until the CDR in February.
A: …I do expect that our cost estimate will be close enough to stand as it for comparison against other bids. Without a design to quote against, or even the specifications for final design (corrector prescription, number of elements, dome ID, housing ID), this is the best I am able to offer under the circumstances.

## Slide 9: Project 2020 resource request
Vendor contract would significantly reduce the resources requested for ME and machine shop.

## Slide 10: Camera Housing Only Matrix (1st unit only)
Note: project was proposed and budgeted as internal build so additional funds would be required for external contract. Example $202k (external) - $32k (internal) = $170k shortfall.

## Slide 11: Discussion points
Sharing NRE with OET reduces our capital cost significantly.
  OET less likely to share if it is an internal MBARI build.
    Support issues & ability to get a 6000 meter housing.
  Cost quote to OET was full 1:1 NRE split. Should we negotiate down to make offer more attractive? We would be trading away our labor compensation* for reducing our capital cost for outside services.
* NRE for camera system (not housing) is $140k, mostly M. Chaffey labor.
OET declines to participate at this time “funding issue”. Discussions will continue through CDR stage.

## Slide 12: More discussion points
Risk of in-house vs contract build.
  Internal resource estimate accuracy?
  In-house technical risk (multiple iterations?).
  Contract build pricing is not guaranteed for all vendors.
    DSP&L will confirm estimate after CDR (late Feb.).
Can MBARI find the additional funds required for an external vendor contract? ~ $123k-$170k