To: M-Team								October 31, 2019

Subject: 2020 Project 902001 4K ROV Camera funding.

From: Mark Chaffey

Background:

This project was proposed and resourced as an internal development project to provide a high quality 4K camera system for our ROV’s. One of the project goals has been to work with a commercial vendor if possible and also to try and find additional users to share the development costs. Once the project was approved internally a request for proposals was sent out to five vendors to design and construct the optical system and housing to our specifications. MBARI will build the balance of the system internally.

In soliciting bids from reputable outside vendors the hope was that they would aggressively price their proposals in return for access to MBARI’s technical contribution and it could result in a commercial product for them. Four bids were received ranging from $155k to $335k for the first housing.

The MBARI cost for designing and building the camera optics and housing internally were also calculated using the project capital and resource requests (with fringe) to use as a comparison.

A meeting was held on October 23, 2019 with the project M-team contact Mike Kelly, and also Doug Au, Andy Hamilton and Francois Cazenave to discuss the relative merits of building in-house or contracting with an outside vendor, and also which vendor would be the preferred awardee if we went that route.

The consensus of the meeting was that if the funds were available, there were advantages to an outside build for the following reasons:

- It reduces the projects technical and resource risk. The project is resourced at 300 hours of Francois Cazenave’s time, but if we run into technical problems this could increase. It also frees up internal engineering time for projects that cannot be out-sourced.

- It provides for on-going operational support for dome replacement, etc. without requiring additional in-house engineering resources over time. This could become more important if we have 4K cameras on both ROV’s.

- Partnering with a reputable commercial vendor substantially increases the likelihood that we are successful in sharing the NRE development costs with another institution.

There also was a consensus that, although they were not the lowest cost bidder, the preferred vendor was Deep Sea Power & Light Inc. for the following reasons:

- They will retain Dr. Paul Remijan, the very skilled optical engineer who designed the i2MAP optical system.

- They provided the most thorough technical proposal and illustrated that they understood the technical risks and the necessary design verification testing to ensure success.

- They have experience with optical domes at pressure that extends back to at least the first dives on the Titanic.

- Their pricing offer was close to the lowest bidder when multiple units are considered.

- They have been a valuable supplier to MBARI for many years and have demonstrated well engineered products and very good customer service.

- They are a well-established company with the resources to be successful.

Additional Funding Request:

The additional funding request for contracting with Deep Sea Power & Light for the camera housing and optics is shown in the table below and totals $173,081 above the original project request spread over two fiscal years.

Note also that there is a substantial savings to MBARI if we are successful in finding another institution to partner and share the NRE costs.

Finally, it should be clear that the project is fully capable and ready to proceed with a total in-house effort, as originally proposed, if that is deemed the preferred course of action.

Mark

We have been in on-going discussions with the Ocean Exploration Trust through Jim Newman and their consulting video engineer Ed McNichol. At one point were close to a verbal commitment, now however there are funding concerns. We have also contacted the Schmidt Ocean Institute through Jason Williams and David Lovalvo at the Global Foundation for Ocean Exploration and these discussions are on-going. It is a realistic possibility that we may find at least one partner institution to share the NRE costs with us before our planned fabrication start in February 2020.