## Sheet1
MBARI LRAUV LARGER NOSE CONES 7-12-21
shop rate | 125
TASK DESCRIPTION | TIME HRS | LABOR COST | MATERIAL DESCRIPTION | MATERIAL COST
Cut provided tube to length | 0.5 | 62.5 | cutter wear | 1
Build spherical mold for nose * | 6 | 750 | foam, epoxy, glass.gel coat | 200
Mold spherical nose piece | 2 | 250 | carbon, epoxy, solvent | 50
Fit and bond nose hemisphere to tube | 0.5 | 62.5 | Proset adhesive, mixing nozzle | 5
Bond G-10 attachment coupling to filament wound tube | 0.75 | 93.75 | Proset adhesive, mixing nozzle | 5
Lightly sand inside of nose cone assembly | 1.5 | 187.5 | sand paper | 3
Paint inside of assembly white | 0.75 | 93.75 | spray paint | 5
Prepare exterior for primer | 1 | 125 | epoxy filler & sand paper | 10
Spray primer | 1 | 125 | masking, primer & solvent | 25
fill sand & fair primer | 3 | 375 | filler & sand paper | 20
Lay out and cut instrument ports, drill attachment holes | 4 | 500 | cutter wear | 5
Mask for top coat | 0.5 | 62.5 | tape & masking paper | 10
Spray top coat | 1 | 125 | paint & solvent | 75
Remove masking & detail paint edges | 1 | 125 |  |  | ESTIMATED TOTAL | 3351.5
[5 empty] | less one time mold cost * | 800
|  | 2937.5 |  | 414 |  | 2551.5
MBARI LRAUV LARGER TAIL CONES
shop rate | 125
TASK DESCRIPTION | TIME HRS | LABOR COST | MATERIAL DESCRIPTION | MATERIAL COST
Male mold machining cost for labor andmaterials unknown.
Apply finish surface to pre-machined male mold for tail cone * | 10 | 1250 | epoxy, glass, gel coat, release | 200
Prep mold, apply release, cut and place carbon fiber | 4 | 500 | carbon, epoxy, peel ply, breather film,breather cloth | 200
prepare for infusion, seal vacuum bag test seals and resin ports | 2 | 250 | bag tape, bag film, tubing | 35
infuse part infusion resin | 1 | 125 | infusion epoxy .5 gallons | 60
Bond G-10 attachment coupling to infused tail cone | 0.75 | 93.75 | Proset adhesive, mixing nozzle | 5
Lightly sand inside of tail cone assembly | 1.5 | 187.5 | sand paper | 3
Paint inside of assembly white | 0.75 | 93.75 | spray paint | 5
Prepare exterior for primer | 2 | 250 | epoxy filler & sand paper | 10
Spray primer | 1 | 125 | masking, primer & solvent | 25
fill sand & fair primer | 4 | 500 | filler & sand paper | 20
Lay out and cut instrument ports, drill attachment holes | 6 | 750 | cutter wear | 5
Mask for top coat | 0.5 | 62.5 | tape & masking paper | 10
Spray top coat | 1 | 125 | paint & solvent | 75
Remove masking & detail paint edges | 1 | 125 | NA |  | ESTIMATED TOTAL | 5090.5
[5 empty] | less one time mold cost * | 1250
|  | 4437.5 |  | 653 |  | 3840.5