## Sheet1
|  | Q1 | Q2 | Q3 | Q4
|  | Validation of Much Faster than Realtime Multi Vehicle Simulation with LRAUV software stack | LRAUV vehicle model infrastructure | LRAUV/ROS interface and integration | LRAUV model tuning, dash integration and Ac data transfer | Selectable Env forcing expansion, and surface comms | Selectable extra sensors for LRAUV
| Task | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Needs budgeted MBARI Support
| Create a basic water column simulation environment, packaged with docker based deployment | M
| Integrate LRAUV software stack | L | [5 empty] | L
| Current world plugin (port wind plugin and extend to positional lookup) |  | M
| Temperature world plugin (positional lookup based) |  |  | M
| Salinity world plugin(positional lookup based) |  |  | M
| Chlorophyll world plugin (positional lookup based) |  |  | M
| Tools for creating scientifically releavant scenarios |  |  | M |  |  |  | S
| Standard interface for science payloads |  |  | M |  |  |  | M
| AUV: 3D Model (provided with CAD or approximation we can open source) | M
| AUV Variable Buoyancy Engine Plugin(Extending existing buoyancy plugin) |  | M
| AUV Mass shifter plugin for attitude control (joint with non-colliding moving mass) |  | M
| AUV Rudder, elevator, thruster | M
| AUV Added Mass simulation (something from UUV Sim to leverage, also added mass matrix is available in existing LRAUV dynamics sim) |  | M
| AUV Emergency Drop Weight plugin |  | S
| LRAUV Vehicle Specific Hydrodynamics Performance Tuning |  |  |  | L
| Acomms: range/bearing |  |  | M
| Acomms: data packet transfer |  |  |  | L |  |  | M
| CTD sensor (temperature, pressure, salinity) |  |  | M
| Fluorometer sensor plugin (Chlorophyll) |  |  | M
| Integration with Tethys Dash M (with support from MBARI) |  |  |  | M
Stage 1 Extensions
| Extend wind plugin to support positional lookup |  |  |  |  | M
| Surface wave emulation ( deploy and improve existing work fro VRX) |  |  |  |  | M
| Surface comms emulation (Iridium, cell) |  |  |  |  | L
| DVL (4 beams @ 1Hz) | [5 empty] | L | S
| Sonar imaging plugin (not currently deployed, being integrated with new WHOI vehicle) | [5 empty] | L | S
| Water sampling device (not sure what this would “capture” we can let it capture all “field phenomena” in a snapshot, but not report it until the end.) | [5 empty] | L | S
| Battery energy simulation | [5 empty] | L
| Days of work: Upper Estimate | 85 | 65 | 120 | 95 | 70 | 160 | 595
| Days of work: Lower Estimate | 50 | 41 | 80 | 50 | 40 | 80 | 341
| FTE Equivalent | 0.36957 | 0.28261 | 0.52174 | 0.41304 | 0.30435 | 0.69565 | 2.587
|  | 0.21739 | 0.17826 | 0.34783 | 0.21739 | 0.17391 | 0.34783
213.75 |  | 145350 | 111150 | 205200 | 162450 | 119700 | 273600 | 1017450
|  | 85500 | 70110 | 136800 | 85500 | 68400 | 136800 | 583110
| ACTUAL SPENDING M1 | 13356 | 26848.13 | 50397.75
| M2 | 36895.5 | 35201.25
| M3 | 38610 | 40000
| M4 | 0
| TOTAL SPENT | 88861.5 | 102049.38 | 50397.75 | 0
| BUDG $ | 56488.5 | 9100.62 | 154802.25 | 162450
| BUDG % | 61.14% | 91.81% | 24.56% | 0%
|  | Min | Max
|  | 1 | 5 | S Size | Up to 1 week
|  | 10 | 15 | M Size | 2-3 weeks
|  | 20 | 40 | L Size | 4-8 weeks
|  |  | 230 | Work Days per Year
Note on B24: Will require mods in LRAUV SimSlate to accommodate -BenYa Ra'anan I added a callout to the right. Can you estimate how much work that will need from your side? -Tully Foote
Note on B27: Already handled by lrauv-application — let's move this to the extension section — I'd love to hear what you have in mind though -BenYa Ra'anan
Note on C51: +byraanan@mbari.org I updated the estimates to be a range which gives us a lower and upper estimates. -Tully Foote Ok, thanks! This looks great — I'll work those estimates into the proposal -BenYa Ra'anan