## List of all deployment
List of docking buoy deployments
Updated: | 2026-01-28
Deployment | Start Date | End date | Duration (days) | Location | Description
1 | 2022-03-24 | 2022-05-13 | 50 | South Monterey Bay | First AUV docking at sea on 6' rod. Mooring used old stretch hose and float. Loss of comms shortly after deployment due to ground found.
2 | 2022-05-25 | 2022-12-08 | 197 | South Monterey Bay | Same system as first deployment, after repairs. Engineering tests. Several successful dockings and first power transfer.
3 | 2023-10-13 | 2024-02-12 | 122 | South Monterey Bay | Upgraded mooring (new stretch hose, new buoy etc). Successful power transfer and battery charging. There was a leaks in the the EM cable and stretch hose, causing a loss of comms.
4 | 2024-06-11 | 2025-01-23 | 226 | North Monterey Bay | Same buoy, new EM cable (we repotted the flooded termination), new strech hose (sent as a replacement by WHOI). On october 4, we recovered the dock, replaced a fuse at sea and redeployed immediately. In the end, there was a ground fault and eventual failure on the stretch hose. The AUV was docked 168 times, data was transfered for the 1st time, battery were charged for several hours.
5 | 2025-05-31 | 2025-08-13 | 74 | North Monterey Bay | Same buoy, same EM cable, new stretch hose, same niobium rod.
6 | 2025-08-14 | 2025-12-15 | 123 | South Monterey Bay | Same as above, different location
|  | Total | 423