Testing Plan, Rev2
AUV Docking on RASP 

List of Milestones:
1. Demonstrate acoustic homing hardware (DAT)
2. Demonstrate AUV homing to a moored transponder
3. Add acoustic telemetery to relay dock heading to AUV
4. Demonstrate AUV an home towards transponder along a prescribed heading
a. Video image of AUV hitting a subsea target (mock dock)
5. Add high-update homing 
6. Add vertical plane homing
7. Dock AUV into stationary dock
8. Move dock to buoy, demonstrate in calm seas
9. Add latch and power/data transfer system 
10. Demonstrate active stabilization of dock using PTO system
11. Demonstrate  AUV docking in Sea State 2


Test 1: DAT Validation, MS#1 –  July 11th - DONE
	This test is designed to validate the basic functionality of the DAT acoustic homing system and the AUV’s DAT interface and logging system.  We will also explore the near-surface performance based on the ratio of valid range/bearing fixes to the number of interrogations at various depths between 5 and 30 meters deep.  We will integrate the (un-calibrated) DAT into the AUV and operate the system offshore Moss Landing.  The AUV will navigate on its own and log the range/bearing data output by the DAT system while making repeated open-loop runs toward a transponder suspended at various depths below a small boat.  

Test 2: Pure Pursuit Homing on Mock Dock, MS#2 – Week of Oct.  17th, earlier if AUV is available.
	During Test 2 we will demonstrate the capability of AUV to autonomously home to a seafloor mounted transponder from an arbitrary heading.  This second test doesn’t require the fast-update rate DAT upgrade or acoustic transmission of the dock heading.  The main task for this test is to port the Dorado-based homing code to the Tethys code-base and test at sea.

Test 3: Directional Homing 1, MS#3 &4 – Week of October 17th
	Test 3 adds the ability for the AUV to home towards the Mock Dock along a prescribed heading.  This test will require Cross-track homing that is analogous to the final approach of an aircraft landing where the aircraft may have to crab into the wind or current to maintain a constant course aligned to the runway.  The approach heading and depth will be hard-coded for this demonstration of 2-D homing.

Test 4: Directional Homing 2 – Week of November 14th
	Test 4 adds the complexity of data telemetry between the Mock Dock and the AUV.  The magnetic heading of the dock will measured and sent to the AUV through the acoustic modem, which is a component of the DAT homing system.  Initially, the compass will be placed on the deck of the ship to maintain directional stability.  The AUV will then home towards the dock using cross-track control to match the vehicle’s heading with the Mock Dock’s heading.  The compass and interface computer will be aboard the small boat. Two cameras will be used to measure the homing accuracy. 

Test 5: Directional Homing 3 – November 21st
	This is a repeat of Test 4, except the compass system will be integrated into the Mock-Dock.

Test 6: Buoy Integration Test 1 – Mid February
	The homing transponder and cameras will be bolted to the buoy system during a normally scheduled test in calm weather.  The AUV will perform homing maneuvers with an offset to minimize crashing into the buoy, cable or winged plate.

Test 7: Docking Test 1 – Mid May
The prototype docking cone and tube will be fitted to the buoy system and tested  during calm weather. 

Test 8: Docking Test 2 – June
	Repeat of Test 1 in rougher sea conditions
	

Test 9: Docking Test 3 – July/August
	Final test to demonstrate AUV docking

