PB Docking Update: 23 April 2012
1. Mock Dock system was recovered
2. Updated buoy is 80% completed
a. New float, new electronics, upgraded charging system
b. Components here and will be ready for wiring on the 25th
3. Dock is 85% completed
a. Subsea housing
i. New endcap out for anodizing
ii. Chassis still in shop – no ano needed
iii. Most components here (Vicor P/S have shipped), needs wiring
b. Ring will be here this week
c. HPU housing  - components here, needs a second connector added and the servo amp mounted and wiring
d. Missing:
i. a few connectors – due anyday
ii. cable strain reliefs
4. AUV
a. Team is focused on Canon operations with Daphne
b. Still struggling with Benthos DAT 
i. 3 degree accuracy is best we can do.  This is OK, but we’re working to improve
1. Better baffleing
2. Stick receiver out the nose at 45 deg down.
c. Altitude integral issue – Rob is working on it
d. A-modem comms abort/retask – Rich 
5. Testing plan – Start May 7th – finish by mid June
a. Completed buoy to be placed on north deck with cable routed under rollup door
i. Solar and comms checkout
b. Dock and AUV in the tank
i. Functionality
6. Deployment – July 11 – finish by mid to late August
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