PB Docking Update: 23 April 2012

- Mock Dock system was recovered

- Updated buoy is 80% completed

  - New float, new electronics, upgraded charging system

  - Components here and will be ready for wiring on the 25th

- Dock is 85% completed

  - Subsea housing

    - New endcap out for anodizing

    - Chassis still in shop – no ano needed

    - Most components here (Vicor P/S have shipped), needs wiring

  - Ring will be here this week

  - HPU housing  - components here, needs a second connector added and the servo amp mounted and wiring

  - Missing:

    - a few connectors – due anyday

    - cable strain reliefs

- AUV

  - Team is focused on Canon operations with Daphne

  - Still struggling with Benthos DAT

    - 3 degree accuracy is best we can do.  This is OK, but we’re working to improve

      - Better baffleing

      - Stick receiver out the nose at 45 deg down.

  - Altitude integral issue – Rob is working on it

  - A-modem comms abort/retask – Rich

- Testing plan – Start May 7th – finish by mid June

  - Completed buoy to be placed on north deck with cable routed under rollup door

    - Solar and comms checkout

  - Dock and AUV in the tank

    - Functionality

- Deployment – July 11 – finish by mid to late August