## Sheet1
|  | Labor (Hours) | [7 empty] | Material | Licensing | Outside Services | Sub-totals |  | Notes
Task |  | Hamilton | Hobson | Cazenave (ME) | ME Total | Jensen (EE) | ME Tech | EE Tech | Machine Shop |  |  |  | Expense | Labor
1st Prototype Design, Fabrication, and Integration | [12 empty] | 0
| Mechanical Design | 16 | 8 | 80 | 104 | [7 empty] | 0 | 104
| Electrical Design | 16 | 8 |  | 24 | 40 | [6 empty] | 0 | 64
| Fabrication | 4 |  | 20 | 24 | 20 | 16 | 16 | 60 | 10000 |  |  | 10000 | 136 |  | $5000 Materials, $5000 Electronics
| Integration and Shoreside Testing | 8 |  | 16 | 24 | 16 | 4 | 4 |  |  |  |  | 0 | 48
| At-sea testing support | [11 empty] | 0 | 0
Task Total |  | 44 | 16 | 116 | 176 | 76 | 20 | 20 | 60 | 10000 | 0 | 0 | 10000 | 352
[5 empty] | 176 | [7 empty] | 10000 | 352 |  | Sum Check Line
2nd Prototype Design, Fabrication, and Integration | [12 empty] | 0
| Mechanical Design | 16 | 8 | 80 | 104 | [7 empty] | 0 | 104
| Electrical Design | 16 | 8 |  | 24 | 40 | [6 empty] | 0 | 64
| Fabrication | 4 |  | 20 | 24 | 20 | 16 | 16 | 80 | 7000 |  |  | 7000 | 156 |  | $5000 Materials, $2000 Electronics
| Integration and Shoreside Testing | 8 |  | 16 | 24 | 16 | 4 | 4 |  |  |  |  | 0 | 48
| At-sea testing support | 8 |  | 8 | 16 | 8 | [6 empty] | 0 | 24
Task Total |  | 52 | 16 | 124 | 192 | 84 | 20 | 20 | 80 | 7000 | 0 | 0 | 7000 | 396
[5 empty] | 192 | [7 empty] | 7000 | 396 |  | Sum Check Line
3rd Prototype Design, Fabrication, and Integration | [12 empty] | 0
| Mechanical Design | 16 | 8 | 80 | 104 | [7 empty] | 0 | 104
| Electrical Design | 16 | 8 |  | 24 | 40 | [6 empty] | 0 | 64
| Fabrication | 4 |  | 20 | 24 | 20 | 16 | 16 | 80 | 6000 |  |  | 6000 | 156 |  | $5000 Materials, $1000 Electronics
| Integration and Shoreside Testing | 8 |  | 16 | 24 | 16 | 4 | 4 |  |  |  |  | 0 | 48
| At-sea testing support | 8 |  | 8 | 16 | [7 empty] | 0 | 16
Task Total |  | 52 | 16 | 124 | 192 | 76 | 20 | 20 | 80 | 6000 | 0 | 0 | 6000 | 388
[5 empty] | 192 | [7 empty] | 6000 | 388 |  | Sum Check Line
Total |  | 148 | 48 | 364 | 560 | 236 | 60 | 60 | 220 | 23000 | 0 | 0 | 23000 | 1136
[5 empty] | 560 | [7 empty] | 23000 | 1136 |  | Sum Check Line