## Sheet1
|  | Labor (Hours) | [7 empty] | Material | Licensing | Outside Services | Sub-totals |  | Notes | Notes
Task |  | Hamilton | Hobson | Cazenave (ME) | ME Total | Jensen (EE) | ME Tech | EE Tech | Machine Shop |  |  |  | Expense | Labor
1st Prototype Design, Fabrication, and Integration | [12 empty] | 0
| Mechanical Design | 8 | 8 | 40 | 56 | [7 empty] | 0 | 56
| Electrical Design | 8 | 4 |  | 12 | 40 | [6 empty] | 0 | 52
| Fabrication | 4 |  | 20 | 24 | 20 | 16 | 16 | 40 | 10000 |  |  | 10000 | 116 |  | $5000 Materials, $5000 Electronics
| Integration and Shoreside Testing | 32 | 24 | 20 | 76 | 32 | 4 | 4 |  |  |  |  | 0 | 116
| At-sea testing support | 8 |  | 8 | 16 | 8 | [6 empty] | 0 | 24
Task Total |  | 60 | 36 | 88 | 184 | 100 | 20 | 20 | 40 | 10000 | 0 | 0 | 10000 | 364
[5 empty] | 184 | [7 empty] | 10000 | 364 |  | Sum Check Line
2nd Prototype Design, Fabrication, and Integration | [12 empty] | 0
| Mechanical Design | 8 | 8 | 60 | 76 | [7 empty] | 0 | 76
| Electrical Design | 8 | 4 |  | 12 | 40 | [6 empty] | 0 | 52
| Fabrication | 4 |  | 20 | 24 | 20 | 16 | 16 | 40 | 7000 |  |  | 7000 | 116 |  | $5000 Materials, $2000 Electronics
| Integration and Shoreside Testing | 32 | 24 | 20 | 76 | 32 | 4 | 4 |  |  |  |  | 0 | 116
| At-sea testing support | 8 |  | 8 | 16 | 8 | [6 empty] | 0 | 24
Task Total |  | 60 | 36 | 108 | 204 | 100 | 20 | 20 | 40 | 7000 | 0 | 0 | 7000 | 384
[5 empty] | 204 | [7 empty] | 7000 | 384 |  | Sum Check Line
3rd Prototype Design, Fabrication, and Integration | [12 empty] | 0
| Mechanical Design | 8 | 8 | 80 | 96 | [7 empty] | 0 | 96
| Electrical Design | 8 | 4 |  | 12 | 40 | [6 empty] | 0 | 52
| Fabrication | 4 |  | 20 | 24 | 20 | 16 | 16 | 40 | 6000 |  |  | 6000 | 116 |  | $5000 Materials, $2000 Electronics
| Integration and Shoreside Testing | 32 | 24 | 20 | 76 | 32 | 4 | 4 |  |  |  |  | 0 | 116
| At-sea testing support | 8 |  | 8 | 16 | 8 | [6 empty] | 0 | 24
Task Total |  | 60 | 36 | 128 | 224 | 100 | 20 | 20 | 40 | 6000 | 0 | 0 | 6000 | 404
[5 empty] | 224 | [7 empty] | 6000 | 404 |  | Sum Check Line
Project and License Management
| Northrop Grumman License Management | 8 |  |  | 8 | [5 empty] | 25000 |  | 25000 | 8 |  | N-G License fee
Task Total |  | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 25000 | 8
[5 empty] | 8 | [7 empty] | 25000 | 8 |  | Sum Check Line
|  | Labor (Hours) | [7 empty] | Material | Licensing | Outside Services | Sub-totals |  | Notes | Notes
Task |  | Hamilton | Hobson | Cazenave (ME) | ME Total | Jensen (EE) | ME Tech | EE Tech | Machine Shop |  |  |  | Expense | Labor
Total |  | 188 | 108 | 324 | 620 | 300 | 60 | 60 | 120 | 23000 | 25000 | 0 | 48000 | 1160
[5 empty] | 620 | [7 empty] | 48000 | 1160 |  | Sum Check Line