## Sheet1
|  | Labor (Hours) | [11 empty] | Material | Licensing | Outside Services | Ship Time |  |  | Sub-totals |  | Notes | Notes
Task |  | Cazenave | Hobson | Hamilton | ME Total | Jensen (EE) | Kieft | Raanan | McEwen | SE Total | ME Tech | EE Tech | Machine Shop |  |  |  | Western Flyer | Rachael Carson | Paragon | Expense | Labor
LRAUV Dock Prototype (design iteration) | [19 empty] | 0
| Mechanical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
| Electrical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
| Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | [5 empty] | 10000 | 0 |  | $5000 Materials, $5000 Electronics
| Integration and Shoreside Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
| At-sea testing support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
Task Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0
[5 empty] | 0 |  |  |  |  | 0 | [9 empty] | 10000 | 0 |  | Sum Check Line
Mars Dock Development | [19 empty] | 0
| Mechanical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
| Electrical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
| Fabrication And Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | [5 empty] | 7000 | 0 |  | $5000 Materials, $2000 Electronics
| Integration and Shoreside Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
Task Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 7000 | 0
[5 empty] | 0 |  |  |  |  | 0 | [9 empty] | 7000 | 0 |  | Sum Check Line
Mars Dock Deployment
| Mechanical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
| Electrical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
| Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | [5 empty] | 6000 | 0 |  | $5000 Materials, $2000 Electronics
| Integration and Shoreside Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
| At-sea testing support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
Task Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 0
[5 empty] | 0 |  |  |  |  | 0 | [9 empty] | 6000 | 0 |  | Sum Check Line
Project and License Management
| Northrop Grumman License Management | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25000 |  |  |  |  | 25000 | 4 |  | N-G License fee
Task Total |  | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 4
[5 empty] | 4 |  |  |  |  | 0 | [9 empty] | 25000 | 4 |  | Sum Check Line
|  | Labor (Hours) | [11 empty] | Material | Licensing | Outside Services |  |  |  | Sub-totals |  | Notes | Notes
Task |  | Hamilton | Hobson | Cazenave (ME) | ME Total | Jensen (EE) |  |  |  |  | ME Tech | EE Tech | Machine Shop | [6 empty] | Expense | Labor
Total |  | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 25000 | 0 | 0 | 0 | 0 | 48000 | 4
[5 empty] | 4 |  |  |  |  | 0 | [9 empty] | 48000 | 4 |  | Sum Check Line