## Sheet1
|  | Labor (Hours) | [10 empty] | Material | Outside Srv | Ship Time |  |  | Sub-totals |  | Notes
Task |  | Hamilton | Cazenave | Hobson | ME | Jensen | EE | Kieft | SE | ME Tech | EE tech McLure | Machinist |  |  | Ship | Time | Cost | Expense | Labor
Design and fabrication of latch for Deep LRAUV
| Mechanical design | 2 | 80 | 8 | 90 | 0 | 0 | 0 | 0 | 16 | 0 | 8 | 500 |  |  |  |  | 500 | 114
| Electrical design | 2 | 0 | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 36 | 0 | 1000 |  |  |  |  | 1000 | 42
| Fabrication and assembly | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 16 | 24 | 80 | 8000 | 2000 |  |  |  | 10000 | 140 |  | Including new actuator from Ultramotion, printed parts, junction box, raw materials
| Integration | 8 | 40 | 4 | 52 | 4 | 4 | 12 | 12 | 8 | 8 | 0 | 2000 |  |  |  |  | 2000 | 84
| Test in test tank | 0 | 16 | 8 | 24 | 4 | 4 | 8 | 8 | 8 | 8 | 0 | 1000 |  |  |  |  | 1000 | 52
| Test at sea | 0 | 16 | 8 | 24 | 4 | 4 | 8 | 8 | 8 | 8 | 0 | 500 |  | Paragon | 2 |  | 500 | 52 |  | Ship time under LRAUV proposal
| Project Management | 4 | 10 | 4 | 18 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 18
Task Total |  | 16 | 182 | 32 | 230 | 16 | 16 | 28 | 28 | 56 | 84 | 88 | 13000 | 2000 | 0 | 2 | 0 | 15000 | 502
[5 empty] | 230 |  | 16 |  | 28 | [8 empty] | 15000 | 502
Mooring recovery, maintenance and redeployment
| February recovery | 0 | 20 | 8 | 28 | 0 | 0 | 0 | 0 | 16 | 8 |  | 500 |  | Shana Rae |  | 3600 | 4100 | 52
| Mooring and dock maintenance and upgrades | 0 | 80 | 4 | 84 | 4 | 4 | 0 | 0 | 40 | 40 | 40 | 12000 | 2000 |  |  |  | 14000 | 208 |  | New EM cable from WHOI, paint, new solar panels, hardware etc
| April deployment Off Davenport | 8 | 20 | 8 | 36 | 0 | 0 | 0 | 0 | 16 | 20 |  | 500 |  | Shana Rae, Paragon | 1 | 3600 | 4100 | 72
| November Recovery | 8 | 40 | 8 | 56 | 0 | 0 | 0 | 0 | 16 | 8 |  | 500 |  | Shana Rae |  | 3600 | 4100 | 80
| Project Management | 4 | 10 | 2 | 16 | 0 | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 16
Task Total |  | 20 | 170 | 30 | 220 | 4 | 4 | 0 | 0 | 88 | 76 | 40 | 13500 | 2000 | 0 | 1 | 10800 | 26300 | 428
[5 empty] | 220 |  | 4 |  | 0 | [8 empty] | 26300 | 428
Build and integrate docking hardware
| Mechanical design | 4 | 200 | 4 | 208 | 0 | 0 | 0 | 0 |  | 0 |  | 500 |  |  |  |  | 500 | 208
| Electrical design | 4 |  | 4 |  | 4 | 4 | 8 | 8 |  | 20 |  | 1000 |  |  |  |  | 1000 | 32 |  | Hardware
| Fabrication and assembly | 4 | 24 | 4 | 32 | 0 | 0 | 0 | 0 | 40 | 40 | 80 | 6000 | 2000 |  |  |  | 8000 | 192 |  | niobium rod and tube, G10, metals, anodizing, printed parts, hardware, junction box, etc.
| Integration And Test | 4 | 16 | 4 | 24 | 4 | 4 | 24 | 24 | 10 | 8 |  | 1000 |  | Paragon | 1 |  | 1000 | 70
| Project Management | 4 | 10 | 4 | 18 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 18
Task Total |  | 20 | 250 | 20 | 282 | 8 | 8 | 32 | 32 | 50 | 68 | 80 | 8500 | 2000 | 0 | 1 | 0 | 10500 | 520 | 0
[5 empty] | 290 |  | 8 |  | 32 | [8 empty] | 10500 | 520
MARS dock design
| Mechanical design | 8 | 120 | 8 | 136 | 0 | 0 | 0 | 0 | 8 | 0 | 16 | 1000 | 1000 |  |  |  | 2000 | 160 | 1024 | 2016 | 2024 | 2000
| Electrical design | 8 | 0 | 4 | 12 | 60 | 60 | 16 | 16 | 0 | 80 | 0 | 1000 |  |  |  |  | 1000 | 168 |  | Test electronics
| Deployment planning | 4 | 16 | 2 | 22 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 34
| Project Management | 4 | 10 | 4 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 18
Task Total |  | 24 | 146 | 18 | 188 | 72 | 72 | 16 | 16 | 8 | 80 | 16 | 2000 | 1000 | 0 | 0 | 0 | 3000 | 380
[5 empty] | 188 |  | 72 |  | 16 | [8 empty] | 3000 | 380
|  | Labor (Hours) | [10 empty] | Material | Outside Srv | Ship Time |  |  | Sub-totals
|  | Hamilton | Cazenave | Hobson | ME | Jensen | EE | Kieft | SE | ME Tech | McLure | Machinist |  |  | Ship | Time | Cost | Expense | Labor
Totals |  | 80 | 748 | 100 | 920 | 100 | 100 | 76 | 76 | 202 | 308 | 224 | 37000 | 7000 | 0 | 4 | 10800 | 54800 | 1830
[5 empty] | 928 |  | 100 |  | 76 | [8 empty] | 54800 | 1830