


Equipment to be recovered:
1. SES (ROV pull pin release of autonomous lander)
2. McLane Sediment trap aka “Trigger trap” (ROV pull pin release of autonomous lander).
3. One current meter (ROV direct recovery and bring up in drawer. Looks like a baseball bat)
4. If possible recover SES weight plate on way up from main dive
5. If there's time after everything else is on board, do a second dive to recover the McLane Trap weight plate.

Order of operations (flexible based on crew input considering conditions):
1. Steam to McLane Sediment trap (“Trigger trap” waypoint— 
36 42.7277N
122 11.2033 W 
882 m depth
Homer 26
Modem faces east
 this is on-the-seafloor lat/long from the ROV when inspecting during deployment)
2. Launch ROV, find Trigger trap 
3. Inspect briefly- check whether it's in the "flow-through" position.
4. Release float line and pull pin on McLane Trap.
5. Pending discussion with pilots- Place sonar reflector on weight plate (and homer if we can get one ready)
6. ROV transit underwater to SES 
36 42.418 N 
122 10.8719 W
884 m depth
Homer 10
Modem is facing NW

7. Inspect SES- check whether it's in the "flow-through" position (if not, Rich will try to talk to it and change it).
8. Recover Current meter (Very close to SES).
9. Release float line and pull pin on SES.
10. If possible, recover SES weight plate. If not, place sonar reflector + homer (whatever pilots prefer)
11. Recover ROV
12. Find and recover SES: VHF: 160.725; Argos 401.65400, argos ID 213423, Homer 10
13. Find and recover McLane trap: VHF: 154.585; Argos 401.64800; Homer 26
15. If time, re-launch and recover McLane weight plates.

Equipment Requested: ROV

Hazardous Materials: Recovering sediment trap with cups that have a total of <3L of <10% formalin. 

MBARI Personnel: All MBARI personnel:

Crissy Huffard
Rich Henthorn
Irene Hu
Paul McGill
Colleen Durkin
Ben Jansen
Denis Klimov


PlannedTrackDesc:
To MARS and back. Lat and longs in cruise plan above.

