## Slide 1
Geo-Sense

## Slide 2
1. How do we take the rapidly developing DAS technology and deploy it as an autonomous instrument?
2. What information can DAS technology provide on the initiation and behavior of sedimentary flows in Monterey Canyon?

## Slide 3
Monterey
1. How do we take the rapidly developing DAS technology and deploy it as an autonomous instrument?
sea-level

## Slide 4
System Diagram
Rover Battery
Sphere
9 kWhr
Rover Battery
Sphere
9 kWhr
Electronics
Housing
DAS
Fiber Optic Cable

## Slide 5
2. What information can DAS technology provide on the initiation and behavior of sedimentary flows in Monterey Canyon?
Moored instruments
Seismometers
MARS cable
Geo-Sense
Water
depth (m)
0
2300

## Slide 6
Budget
Monterey
  DAS interrogator - $55,000
  Battery package (20 kWhrs of Li primary batteries) - $20,000
  Underwater cable - $20,000
  FO connectors - $10,000
  Beacons (if required) - $5,000
  Frame materials and mechanical components - $3,000
  Travel (to Sintela HQ) - $1,645

## Slide 7
Personnel
Team
Monterey
Science
Charlie Paull, Roberto Gwiazda, Eve Lundsten, John Ryan
Engineering
Alana Sherman (400 hrs) – project manager
Aaron Schnittger (240 hrs)
Denis Klimov (280 hrs)
Paul McGill (280 hrs)
Rich Henthorn (120 hrs)
Yanwu Zhang (20 hrs)
DMO
Knute Brekke (80 hrs)
DMO-Marine Operations Support (160 hrs)

## Slide 8
Ship requirements
Monterey
  R/V Packard – 2 days for testing in October 2024 (?)

## Slide 9
Work plan 2024
Monterey
Task | Month (2024) |  |  |  |  |  |  |  |  |  |  | 
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Question 1 |  |  |  |  |  |  |  |  |  |  |  | 
Identify latest suitable instruments |  |  |  |  |  |  |  |  |  |  |  | 
Develop a conceptual design of a portable DAS system |  |  |  |  |  |  |  |  |  |  |  | 
Carry out SWOT analysis |  |  |  |  |  |  |  |  |  |  |  | 
Conduct a design review |  |  |  |  |  |  |  |  |  |  |  | 
Question 2 |  |  |  |  |  |  |  |  |  |  |  | 
Critical design review and detailed design |  |  |  |  |  |  |  |  |  |  |  | 
Selection of appropriate deployment and recovery protocol |  |  |  |  |  |  |  |  |  |  |  | 
Identify components already available at MBARI |  |  |  |  |  |  |  |  |  |  |  | 
Procurement of interrogator, cable and batteries |  |  |  |  |  |  |  |  |  |  |  | 
Assembly of prototype |  |  |  |  |  |  |  |  |  |  |  | 
Testing of prototype in the lab and field |  |  |  |  |  |  |  |  |  |  |  | 
Others |  |  |  |  |  |  |  |  |  |  |  | 
Permitting issues |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 10
Work plan 2025
Monterey
  Deployment/recovery of DAS prototype in January – February 2025 in Monterey Canyon

## Slide 11
Deployment/recovery strategy
Monterey