## Slide 1: Geo-Sense Project Update May 2025
Aaron Micallef, Alana Sherman, Aaron Schnittger, Paul McGill, Denis Klimov, Bryan Touryan-Schaefer, Rich Henthorn, and Rebecca Englert

## Slide 2: Many thanks to the team!!
Notes: Randy, kavi, josh carson, andy, ben dmo, Andrew mckee, knute, carson crew, charlie

## Slide 3: Geo-Sense: Science Motivation
Can we capture high-resolution measurements of seafloor processes in areas with no connection to shore power or communications?

## Slide 5: Key Questions for Geo-Sense Project
1. How do we take the rapidly developing DAS technology and deploy it as an autonomous instrument?
2. What information can DAS technology provide on the initiation and behavior of sedimentary flows in Monterey Canyon?

## Slide 6: More Science Motivation: SeismoSands, November – March 2025
Moored instruments
Seismometers
MARS cable
Water
depth (m)
0
2300
What information can DAS technology provide on the initiation and behavior of sedimentary flows in Monterey Canyon?

## Slide 7: Initial Geo-Sense Concept
Monterey

## Slide 8: The Challenges
Commercial DAS instruments are large
Commercial DAS instruments are power hungry (>100 Watts)
DAS creates huge amounts of data (1.8TB/day)
Sintela, a commercial company located in the UK, was interested in developing a lower-power, stand-alone DAS
Lower power <30 Watts
External Collaboration
Notes: MARS DAS

## Slide 9: Geo-Sense Timeline to Participate in SeismoSands
Project Approved for 2024
From our proposal:
  Components procured June 2024
  Prototype assembled Sept 2024
  2 days on the R/V David Packard after September 2024 to test the deployment/recovery strategy.
  4 days on the R/V David Packard in February–March 2025 to deploy and recover the prototype and cable.

## Slide 10: How to get it done quickly..
Reuse
  Pressure housings
  Battery design
  Technology

## Slide 11: Technical Challenges
Cable design and selection
Deployment and recovery plan
Weight due to batteries

## Slide 12: Deployment Method

## Slide 13: DAS
DAS
1 km armored FO cable
Cable
Termination
FO Core
Oil-compensated
Junction box –
Fiber breakout
Strain
Relief
Black
Hole
Term.

## Slide 14: Geo-Sense Timeline
Project approved for 2024
From our proposal:
  Components procured June 2024
  Prototype assembled Sept 2024
  2 days on the R/V David Packard after September 2024 to test the deployment/recovery strategy.
  4 days on the R/V David Packard in February–March 2025 to deploy and recover the prototype and cable.

## Slide 15: Geo-Sense Timeline by Summer 2024
From our proposal:
  Components procured June 2024
    Cable due 9/25/24
    DAS expected by 11/1/24
  Prototype assembled Sept 2024 Dec 2024
  2 days on the R/V David Packard after September 2024 to test the deployment/recovery strategy.
  4 days on the R/V David Packard in February–March 2025 to deploy and recover the prototype and cable. Begin begging for ship days on the R/V Rachel Carson

## Slide 16: Geo-Sense Timeline by Dec 31, 2024
From our proposal:
  Components procured June 2024
    Cable due 9/25/24
    Terminated cable arrived Dec 17, 2024
    DAS expected by 11/1/24
    DAS arrived Dec 27, 2024…with a better one on the way
  Prototype assembled Sept 2024 Dec 2024
  mid-Jan 2025
  2 days on the R/V David Packard after September 2024 to test the deployment/recovery strategy.
  4 days on the R/V David Packard in February–March 2025 to deploy and recover the prototype and cable. R/V Carson days Jan 24, 27, 28

## Slide 17: Strain Relief – Jan 16 8 days until deployment
Notes: 24- 36 hours for initial cure

## Slide 18: Jan 16 – 8 days until deployment
Slight Delay….

## Slide 19: Sunday, Jan 19, begin potting strain relief

## Slide 20: Mob day – Jan 23 – 1 day until deployment
Strain relief is a little sticky… but the instrument is working
We are ready to go!
Notes: Noro virus
Denis and Aaron stay late

## Slide 21: Mob Night – until 11 p.m. Jan 23

## Slide 22: Friday, Jan 24 Deployment Day

## Slide 23: 6:30 am Pre-deployment Checks
Notes: NoroVirus, smell

## Slide 24: 8 am Deployment Day… Something smells burnt
Notes: First Zoom with Sintela was 11 am

## Slide 25: Smoking Gun – Literally!

## Slide 26: Also that morning… Strain Relief Part 2: Revenge of the Potting Compound

## Slide 27: Chipping away at the problem

## Slide 28: Getting back to the DAS…

## Slide 29: Where is that other DAS…

## Slide 30: New part to the rescue

## Slide 31: Saturday Morning, Jan 25

## Slide 32: Saturday Jan 25, 9 am… And our part is…
!!?@#$#

## Slide 33: Saturday mid-morning Calling in the pros!

## Slide 34: Let the Zoom begin – 8 hour time difference

## Slide 35: We removed the bad part but …
Notes: Sintela sent us a rework schedule with things to remove and where to attach wires, but each time we powered up the board, it was still shorted (-5V and +12V shorted to ground). We kept taking off more parts until the whole section was empty. Then we realized the problem was somewhere else on the board. We used a thermal camera to find the problem. Video. We then started to use Denis’ dental drill to excavate into the board until we could clear the short. This board would normally be trash, but that was not an option

## Slide 36: We removed the bad part but …
Notes: Sintela sent us a rework schedule with things to remove and where to attach wires, but each time we powered up the board, it was still shorted (-5V and +12V shorted to ground). We kept taking off more parts until the whole section was empty. Then we realized the problem was somewhere else on the board. We used a thermal camera to find the problem. Video. We then started to use Denis’ dental drill to excavate into the board until we could clear the short. This board would normally be trash, but that was not an option

## Slide 37: Grinding away at the problem

## Slide 38: Strain Relief Part 2

## Slide 39: Morale…

## Slide 40: Sunday, Jan 26

## Slide 41: Early Sunday…Collateral Damage
Notes: Replace Nano jetson- linux machine, custom serial adapter
Configure
Set up network collab agreement ( Joe in for reviews)
Left Sunday program and test instrument remotely
10 hour zoom on Sunday 8 am – 6 pm PST

## Slide 42: Monday, Jan 27
There’s a problem with the clock!
Reassemble
Mob part 2
Notes: Phase lock loop chip, clock drift 5%

## Slide 43: Tuesday, Jan 28 Deployment Day

## Slide 44: Tuesday, Jan 28 Deployment Day (Again!)

## Slide 46: Jan 27 – Deployment Date
Notes: Telepresence and deep sea connect - productively involved

## Slide 47: Ice cream Time

## Slide 48: Feb 6 – 10 days later Check for Data

## Slide 49: Recovery – Feb 28

## Slide 50: But we got data – 9 days worth!!
Notes: 60 GB

## Slide 51: And we got the new DAS

## Slide 52: Data are dominated by big waves
Notes: The most dominant signal we see is from the ocean surface waves

## Slide 53: Seismic wave picking
Predicted distance
49.6 km
Time (sec)
Notes: With the right filtering, we can hone in on more interesting signals like earthquakes. This data is high-pass filtered. Earthquakes have a characteristic (pWave – pressure wave going through the body of the earth, and the s wave is a surface wave that is like an ocean wave. The p-wave travels faster. Because these waves travel at different velocities, you can determine the distance to the source by measuring the time between p-wave and s-wave arrivals. By making this measurement at multiple locations, you can determine the location of the epicenter.

## Slide 54: Nailed it!
Actual distance
49.5 km
Notes: So close that we repeated this with a different earth quake and it matched

## Slide 55: Spectrograms and sounds: On deck
Notes: This is sped up ten times so we can hear them. Impact drill most likely

## Slide 56: Spectrograms and sounds: Alien spaceship

## Slide 57: Way more data processing to go…

## Slide 58: Up Next
Bore hole test site, Norway
Back to the Canyon

## Slide 59: Thanks!!

## Slide 60: Questions

## Slide 61: There is a problem with the cable

## Slide 62: Spectrograms and sounds: M2.34 earthquake

## Slide 63
limited availability of submarine cables and access to dark fibers and interrogators
submarine cables tend to be located away from seafloor processes of interest
Problems

## Slide 64: Key Elements: DAS, Cable, Deployment Scheme
Rover Battery
Sphere
9 kWhr
Rover Battery
Sphere
9 kWhr
Electronics
Housing
DAS
Fiber Optic Cable

## Slide 65: Enabling Technology: Distributed Acoustic Sensing (DAS)
Ide et al. (2021)
Channels
Variation of strain (temperature) along cable
Dates (Jan 2020)
Notes: limited availability of submarine cables and access to dark fibers and interrogators
submarine cables tend to be located away from seafloor processes of interest