## 902312
902312 (Seafloor processes)
[8 empty] | Expenses ($) | Staff (hrs)
Activity | Description | Note | RV Packard (days) | RV Carson (days) | Paragon (days) | Equipment | Timing
Seismosand
Seismosand | Repeat mapping of canyon head |  |  | 2 (10 hr) |  | Mapping AUV | February 2025 |  | ?
Seismosand | Repeat mapping of canyon head |  |  |  | 2 (8 hr) | Pole-mounted MBES | February 2025 |  | Figurski (16)
General
LASS survey (Tubeworm Slump) | Postponed from 2024? |  | 6 (24 hr) |  |  |  | May 2025 |  | Martin (144) | Kecy (144) | Risi (144)
LASS survey (Santa Monica Mound) | Postponed from 2024? | Requested by Caress in 901101 |  |  |  |  | May 2025
Outreach | GEOHAB conference | Key West | [5 empty] | 3000
Outreach | Animations and illustrations | [6 empty] | 10000
MBARI postdoc | Travel, dissemination, consumables | [6 empty] | 10000
Software ? | Kingdom annual license | [6 empty] | 12000
Publication costs | [7 empty] | 5000
Laboratory and office consumables | [7 empty] | 7500
Testing and training of DORISS |  |  | 1 (mob), 1 survey | 1 (mob), 1 survey |  | 2 days (Ricketts), 2 days (Ventana) |  | 0 | Kirkwood (x) | Walz (x)
Antarctica | SOI cruise (if funded)
Rental of generator | [7 empty] | 2000
Consumables | [7 empty] | 5000
Shipping of MBARI sensors | [7 empty] | 30000
Shipping of samples | [7 empty] | 10000
Insurance participants | [7 empty] | 1500
Travel costs (MBARI personnel) | 5 people | [6 empty] | 12500
Analyses | Ion chromatography | [6 empty] | 4000
Analyses | Gas chromatography | [6 empty] | 4000
Analyses | XRF | [6 empty] | 6000
Analyses | Geochronological analyses | [6 empty] | 30000
Analyses | Isotopes | [6 empty] | 6000
LRAUV project
Rental of boat in Santa Barbara |  | could be replaced with days on Packard
TOTAL | [7 empty] | 158500

## 902401
902401 (Geo-Sense)
[8 empty] | Expenses ($) | Staff (hrs)
Activity | Description | Note | RV Packard (days) | RV Carson (days) | Paragon (days) | Equipment | Timing
Seismosand
Survey | Deployment, assessment, recovery |  | 3 (24 hr) | 1 (10 hr) |  | Ventana (1 day) | 15th January - 12th February
Santa Barbara seeps
Survey | Deployment, recovery | (excluding transit) | 2 (24 hr) |  |  |  | December
Future surveys
Axial seamount | Feasibility study (OOI) | we might need to choose one |  |  |  |  | January-June
Link with wave energy | Feasibility study (OOI) | [5 empty] | January-June
Deployment in boreholes | IODP 406 (New England) | [5 empty] | January-June
General
Spare cable | with enhanced backscatter | awaiting quote | [5 empty] | 40000
FO connectors | [7 empty] | 10000
Cable/rubber molded connectors | [7 empty] | 5000
Batteries | [7 empty] | 30000
NRE |  | request quote (Sintela)
TOTAL |  |  | 4 | 1 |  |  |  | 85000

## 902402
902402 (CSEM)
[8 empty] | Expenses ($) | Staff (hrs)
Activity | Description | Note | RV Packard (days) | RV Carson (days) | Paragon (days) | Equipment | Timing
Arctic expedition
Travel | Flights (1000), hotel (500), subsistence (500), taxi (300) | [6 empty] | 2300
Freight | CSEM + winch | awaiting quote | [5 empty] | (might be covered by Charlie)
Polar suit | https://www.landfallnavigation.com/catalog/product/view/id/5952.html?gad_source=1&gclid=Cj0KCQjw_-GxBhC1ARIsADGgDjtlBpRR37OKZhw9J5YqsO2MbDNaN6MOFVMgLAgg_xV6g6e8MlL_bZ8aAqZoEALw_wcB#132=1301 | [6 empty] | 600
CSEM development
Feasibility study | [7 empty] | 0 | Sherman (100) | McGill (80) | Trauschke (160) | Brekke (80) | Voigtlander (150)
TOTAL | [7 empty] | 2900