## 902312
902312 (Seafloor processes)
[6 empty] | Expenses ($) | Staff (hrs)
Activity | RV Packard (days) | RV Carson (days) | Paragon (days) | Equipment | Timing |  | Sherman | Schnittger | Klimov | Henthorn | Touryan-Schaeffer | Others | Hobson | Shemet | Wahl | Voigtlander | M Tech | Martin | Kecy | Risi | Conway
1. Antarctica (DQ 24-43) |  |  |  |  | January 2026
Consumables | [5 empty] | 500
Insurance | [5 empty] | 500
Ion chromatography | [5 empty] | 1500
Gas chromatography | [5 empty] | 2500
Geochronological analyses | [5 empty] | 3500
Isotopes | [5 empty] | 2500
SWAN CSEM |  |  |  | Black and blue winches | [11 empty] | 200
2. French Polynesia (DQ 25-19) |  |  |  |  | December 2026
Travel costs incl ship gear | [5 empty] | 4000
Analyses | [5 empty] | 1000
Land transport | [5 empty] | 500
3. Amazon Canyon (DQ 25-04) |  |  |  |  | May 2026
Shipping of samples | [5 empty] | 2500
Sample analyses (geochronology, elemental analyses, organic carbon analyses, Fourier-transform infrared spectroscopy) | [5 empty] | 10000
Moorings (return shipping to Fortaleza) |  |  |  | Mooring components |  | 10000 | [14 empty] | 120
4. Tubeworm Slump |  |  |  |  | November 2026
LASS survey | 6 | [16 empty] | 144 | 144 | 144
International meeting (South Africa) |  |  |  |  | July 2026
Travel | [5 empty] | 3000
Registration, accommodation, subsistence | [5 empty] | 1000
General expenses
Lab consumables, materials and supplies, field equipment, memberships | [5 empty] | 10000
Research specialist expenses (conference participation) | [5 empty] | 4000
Social media manager | [5 empty] | 6000
TOTAL | 6 |  |  |  |  | 63000 | [9 empty] | 200 |  | 144 | 144 | 144 | 120

## 902401
902401 (Geo-Sense)
[6 empty] | Expenses ($) | Staff (hrs)
Activity | RV Packard (days) | RV Carson (days) | Paragon (days) | Equipment | Timing |  | Sherman | Schnittger | Klimov | Henthorn | Touryan-Schaeffer | Others | Hobson | Shemet | Wahl | Voigtlander | M-Tech | Martin | Kecy | Risi | Conway
Aegean |  |  |  |  | September 2026
1.1 Kolumbo | [6 empty] | 120 | 80 | 40 | 40 | 120 | 80 |  |  |  |  | 120
Travel | [5 empty] | 8000
Accommodation | [5 empty] | 1000
Subsistence | [5 empty] | 500
Shipping | [5 empty] | 26000
1.2 Milos |  |  |  |  | September 2026 |  | 80 | 120 | 40 | 40 |  | 40
Travel | [5 empty] | 500
Accommodation | [5 empty] | 2000
Subsistence | [5 empty] | 750
Shipping | [5 empty] | 5000
Power consumption | [5 empty] | 100
Diving company services | [5 empty] | 2000
3. LRAUV test |  |  | 3 | LRAUV | January 2026 |  | 100 | 100 | 100 | 40
Housing | [5 empty] | 1500
Penetrator and connectors | [5 empty] | 2600 | [6 empty] | 30 | 30
4. System maintenance and upgrades |  | 3 |  |  | January 2026 |  | 120 | 100 | 120 | 40 |  | 80 |  |  |  |  | 80
TOTAL |  | 3 | 3 |  |  | 49950 | 420 | 400 | 300 | 160 | 120 | 200 | 30 | 30 |  |  | 200

## 902402
902402 (CSEM)
[7 empty] | Expenses ($) | Staff (hrs)
Activity | Description | RV Packard (days) | RV Carson (days) | Paragon (days) | Equipment | Timing
ON PAUSE | ONLY DATA ANALYSES
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0

## Combined
[6 empty] | Expenses ($) | Staff (hrs)
Activity | RV Packard (days) | RV Carson (days) | Paragon (days) | Equipment | Timing |  | Sherman | Schnittger | Klimov | Henthorn | Touryan-Schaeffer | Others | Hobson | Shemet | Wahl | Voigtlander | M Tech | Martin | Kecy | Risi | Conway
1. Antarctica (DQ 24-43) |  |  |  |  | January 2026
Consumables | [5 empty] | 500
Insurance | [5 empty] | 500
Ion chromatography | [5 empty] | 1500
Gas chromatography | [5 empty] | 2500
Geochronological analyses | [5 empty] | 3500
Isotopes | [5 empty] | 2500
SWAN CSEM |  |  |  | Black and blue winches | [11 empty] | 200
2. French Polynesia (DQ 25-19) |  |  |  |  | December 2026
Travel costs incl ship gear | [5 empty] | 4000
Analyses | [5 empty] | 1000
Land transport | [5 empty] | 500
3. Amazon Canyon (DQ 25-04) |  |  |  |  | May 2026
Shipping of samples | [5 empty] | 2500
Sample analyses (geochronology, elemental analyses, organic carbon analyses, Fourier-transform infrared spectroscopy) | [5 empty] | 10000
Moorings (return shipping to Fortaleza) |  |  |  | Mooring components |  | 10000 | [14 empty] | 120
4. Tubeworm Slump |  |  |  |  | November 2026
LASS survey | 6 | [16 empty] | 144 | 144 | 144
International meeting (South Africa) |  |  |  |  | July 2026
Travel | [5 empty] | 3000
Registration, accommodation, subsistence | [5 empty] | 1000
General expenses
Lab consumables, materials and supplies, field equipment, memberships | [5 empty] | 10000
Research specialist expenses (conference participation) | [5 empty] | 4000
Social media manager | [5 empty] | 6000
1.1 Kolumbo |  |  |  |  | September 2026 |  | 120 | 80 | 40 | 40 | 120 | 80 |  |  |  |  | 120
Travel | [5 empty] | 8000
Accommodation | [5 empty] | 1000
subsistence | [5 empty] | 500
Shipping | [5 empty] | 26000
1.2 Milos |  |  |  |  | September 2026 |  | 80 | 120 | 40 | 40 | 0 | 40
Travel | [5 empty] | 500
Accommodation | [5 empty] | 2000
Subsistence | [5 empty] | 750
Shipping | [5 empty] | 5000
Power consumption | [5 empty] | 100
Diving company services | [5 empty] | 2000
3. LRAUV test |  |  | 3 | LRAUV | January 2026 |  | 100 | 100 | 100 | 40 | 0
Housing | [5 empty] | 1500
Penetrator and connectors | [5 empty] | 2600 | [6 empty] | 30 | 30
4. System maintenance and upgrades |  | 3 |  |  | January 2026 |  | 120 | 100 | 120 | 40 |  | 80 |  |  |  |  | 80
TOTAL | 6 | 3 | 3 |  |  | 112950 | 420 | 400 | 300 | 160 | 120 | 200 | 30 | 30 | 0 | 200 | 200 | 144 | 144 | 144 | 120