## Slide 1
CSEM

## Slide 2
1. To reconfigure and test a recently developed surface-towed CSEM system
2. To assess if/how an ROV- or AUV-based CSEM system can/should be built at MBARI to carry out repeat surveys of fluid flow systems at high spatial resolution and in a wide range of water depths

## Slide 3
To reconfigure and test a recently developed surface-towed CSEM system

## Slide 4
To reconfigure and test a recently developed surface-towed CSEM system

## Slide 5
Budget
Monterey
  Reconfiguration of SWAN system - $30,000
  Permitting and contingency plan - $5,000
  4 ship days + 4 mob days - $22,000
  Freight costs and customs - $10,000
  Consumables - $5,000

## Slide 6
Personnel
Team
Monterey
Science
Charlie Paull, Roberto Gwiazda
Engineering
Alana Sherman (230 hrs) – project manager (transferred to new hire?)
Jon Erickson (360 hrs)
Paul McGill (80 hrs)
Dave Caress
DMO
Erik Trauschke (40 hrs)
Eric Fitzgerald (20 hrs)
Erich Rienecker (80 hrs)
Knute Brekke (80 hrs)

## Slide 7
Ship requirements
Monterey
  R/V Shana Rae or Fulmar
  4 ship days + 4 mob days in September 2024

## Slide 8
Work plan 2024
Monterey
Task | Month (2024) |  |  |  |  |  |  |  |  |  |  | 
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Synthetic modeling for Canadian Arctic |  |  |  |  |  |  |  |  |  |  |  | 
Adapt MBARI winch for deployment of SWAN system, or procure one |  |  |  |  |  |  |  |  |  |  |  | 
Rienecker visit to GEOMAR |  |  |  |  |  |  |  |  |  |  |  | 
Delivery of SWAN system to MBARI |  |  |  |  |  |  |  |  |  |  |  | 
Adapt SWAN system for deployment |  |  |  |  |  |  |  |  |  |  |  | 
Execute joint test and science survey in Monterey Bay |  |  |  |  |  |  |  |  |  |  |  | 
Process and invert CSEM data |  |  |  |  |  |  |  |  |  |  |  | 
Others |  |  |  |  |  |  |  |  |  |  |  | 
Permitting issues |  |  |  |  |  |  |  |  |  |  |  | 
Liability and insurance issues |  |  |  |  |  |  |  |  |  |  |  | 
Identify vessel and book |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 9
Work plan 2025
Monterey
  Deployment/recovery of SWAN in the Canadian Arctic – August 2025

## Slide 10
Change in plans?
Risks related to towing close to shore (?)