902712 Ventana FO Can replacement Project Work Flow outline	June 2026   	Osborne

The first phase of this project would officially start in Jan 2027.  We plan to begin the process of identifying the technology we hope to implement to meet the FO Can functional requirements during 1/2Q2027.  The functional requirements will be documented and identified prior during the 3-4Q2026.

Ideally by end of 2-3Q2027, the design will be mostly complete and we would be able to start purchasing connectors, housing raw material, Mux hardware, etc and start the fabrication of the pressure housing and internal electronics before year end, 2027.  Once the pressure housing is complete and the connectors installed we would do pressure testing prior to population of internals.

The new housing and penetration head should be complete by 1Q2028 and we would start integration to the backplane structure and associated internal wiring fixtures.  The Focal 907X mux would be partially available prior to this time (2027) and would be purchased according to what cards are available.  The remaining cards would be purchased early 2028 and integrated upon arrival.

The plan to split the work over a two year period allows the budget to be spread out for capital purchases as well as labor loads.  Essentially the connectors, housing materials and some Focal Mux cards would be purchased first year.  The second year would involve the electronic backplane boards, switching cards, power supplies and remaining  Focal Mux cards.  Focal is designing a next generation multiplexer which coincides nicely with this projects milestone dates.  We currently have a NDR agreement with Focal not to share any of the information regarding this new hardware that is expected to be supported till 2050.  This budget plan equates to approximately 125k$ of hardware purchased each project year, 2027 and 2028.  Spares could be purchased in 2029-30 to further spread out the monetary point loading.

The system build would be finalized late 4Q2028 and then installed during the Carson second big yard period projected 1Q-2Q2029.  The ROV would stay in Bay 1 and undergo the upgrade while the ship was at the yard.  We would need an extra week of time to test the control room interfaces once the ship arrived back to MBARI.  It might also be necessary to travel to the yard for a week or two at most in order to install the topside system upgrades prior to ship arriving back to MBARI.    As many interfaces as practical and possible would be kept the same in order to minimize integration time and maximize test time and focus on actual upgrades and enhancements.

We plan to involve Paul McGill for general consulting on the internal layout/design we plan to implement to meet the functional requirements.  Paul will also review the new design details interfacing with the existing ground fault detection system he and I have worked on together perfecting for years.  Paul has talent in helping me keep feature creep to a minimum while maintaining a high level of future proofing for the features required.

Attached is a rough budget for the labor and hardware currently estimated as close as possible.  There are minimal risks to the schedule not being met due to the newly designed and delivered Focal hardware.  Focal has been an exceptionally reliable manufacturer of Mux hardware and although there is some concern with being one of the first customers for the next generation system it is minimal due to their strong reputation.