## Sheet1
Year | Quarter | Task | Parts Cost
2027 | 1 | Design + PDR & CDR
| 1 | Finalize system block diagram level design
| 1 | Hold Preliminary Design Review
| 1 | Purchase Ti for housing and endcaps | 25158
| 1 | Submit machining job for housing + endcaps
| 1 | Order Scorpion/Seaconn connectors | 20400
| 1 | Order ISE Fiber harness | 8000
| 2 | Design backplane pcb
| 2 | Design micro pcb
| 2 | Design video switch pcb
| 3 | Design video isolation pcb
| 3 | Specify all fiber optic hardware
| 3 or 4 | Pressure test housing (Pt. Hueneme) | 4000
| 4 | Hold Critical design review
| 4 | Send all pcbs out for fabrication | 5600
| 4 | Order Vicor modules | 4000
|  | 2027 Parts Total Cost | 67158
2028 | 1 | Begin Build
| 1 | Populate all pcbs | 6000
| 1 | Populate (wires only) connectors on endcap
| 1 | Order Focal 907 stack | 75000
| 1 | Order CWDM for telemetry fiber | 8000
| 1 | Order Focal Mux DWDM | 40000
| 1 | Order new HDSI cameras to replace NTSC | 16500
|  | Order FO connectors, cables, and whips | 15000
| 2 | Test Individual pcbs
| 2 | Integrate pcbs
| 3 | System integration (bench)
| 3 | Order any misc hardware | 4000
|  | 2028 Parts Total Cost | 164500
2029 | 1 | Integration onto ROV Ventana
| 1 | Misc mounting hardware or replacement parts | 20000
| 2 | Install new FO Can onto Ventana
| 2 or 3 | Non-science day at-sea testing of can
| 3 or 4 | Ready for science
|  | 2029 Parts Total Cost | 20000
|  | Total Project Cost | 251658