## Tasks+Parts
Ventana FO Can upgrade 902712
Year | Quarter | Task | Parts Cost
2027 | 1 | Design + PDR & CDR
| 1 | Finalize system block diagram level design
| 1 | Purchase Ti for housing and endcaps | 25158
| 1 | Submit machining job for housing + endcaps
| 1 | Order Scorpion/Seaconn connectors | 20400
| 1 | Order ISE Fiber harness x 2 | 16000
| 1 | Order FO bulkhead connectors | 15000
| 2 | Hold Preliminary Design Review
| 2 | Design backplane pcb
| 2 | Design micro pcb
| 2 | Design video switch pcb
| 3 | Design video isolation pcb
| 3 | Specify all fiber optic hardware
| 3 or 4 | Pressure test housing (Pt. Hueneme) | 4000
| 4 | Hold Critical design review
| 4 | Send all pcbs out for fabrication | 5600
| 4 | Order Vicor modules | 4000
|  | 2027 Parts Total Cost | 90158
2028 | 1 | Begin Build
| 1 | Populate all pcbs | 6000
| 1 | Populate (wires only) connectors on endcap
| 1 | Order Focal 907 stack | 75000
| 1 | Order CWDM for telemetry fiber | 8000
| 1 | Order Focal Mux DWDM | 40000
| 1 | Order new HDSI cameras to replace NTSC | 16500
| 1 | order FO cables and whips | 15000
| 2 | Test Individual pcbs
| 2 | Integrate pcbs
| 3 | System integration (bench)
| 3 | Order any misc hardware | 4000
|  | 2028 Parts Total Cost | 164500
2029 | 1 | Integration onto ROV Ventana
| 1 | Misc mounting hardware or replacement parts | 20000
| 2 | Install new FO Can onto Ventana
| 2 or 3 | Non-science day at-sea testing of can
| 3 or 4 | Ready for science
|  | 2029 Parts Total Cost | 20000
|  | Total Project Cost | 274658

## Labor
Ventana FO Can resource estimate summary
|  | 2027 | 2028 | 2029
Machinist | Ray Thompson | 200 | 160 | 20 | 2027 build penetration head, backplane, internal fixtures.
2028 build barrel, endcap, final internal fixtures, tie rods, misc.
EE Tech | Jose Group | 320 | 500 | 40 | 2027 populate bulkheads, install, land wiring harness, build backplane, card stuffing,
2028 continue can internal build and install mux and rest of electronics
ME Tech | Coenen Group | 120 | 120 | 40 | assistance with pressure testing, can internal fixture manuf, annodizing, backplane assembly,
ME | Hamilton/Tucker | 120 | 40 | 10 | Pressure vessel and mechanical design checks, stress analysis, FEA modeling, thermal design
EE | Eric Martin | 40 | 40 | 10 | Discussions of trade offs on how to populate the can
| Chad Kecy | 160 | 200 | 160 | designs for backplane or switching cards, power layout, bus design.
| Paul Roberts | 40 | 60 | 20 | assessment of new fiber + AC connector
| George Stern | 120 | 160 | 20 | designs for backplane, switching cards, power layout, bus design
| Paul McGill | 0 | 0 | 0 | Consulting, design reviews, ground fault system support, system integration reviews
Software | Mike Risi | 80 | 40 | 10 | FO micro software or other firmware changes
| Totals | 1200 | 1320 | 330