## To Do
Sub-assembly | Resp Party | Also need | Task | Notes
HOUSING:
Housing | GM | Mike | [GM, shop] Need housing. | 1 soon, 2nd before May 17
Housing | GM | Shop | [GM, shop] Need another topFlange. Have blank, but no holes drilled. | WO 4959
Housing | GM |  | [GM] Remove socket flat head screws from bottom flange. | Submitted to shop
Housing | GM |  | Make sure housings and top plates to be anodized fit
Housing | GM |  | Anodize housing and top plates
Top Plate |  |  | TOP PLATE:
Top Plate | GM |  | Need 2nd top plate and associated parts. | half kitted
Top Plate | GM |  | Probably missing some 1/4-20 helicoils | Can use stainless or phosphor bronze.
HYDRAULICS:
Hydraulics |  |  | oildyneStand4:
Hydraulics |  |  | Screws that attach oildyneStandUpperPlate to oildyne pump need to be 10-24
Hydraulics |  |  | 91780A081_Alum.... needs to indicate that it is an altered item
Hydraulics |  |  | (maybe the altered part needs to have the part name as an assembly, and the parts that make up that assembly is the COTS item?)
Hydraulics
Hydraulics |  |  | motorizedValveSmall:
Hydraulics |  |  | SwagelokSS-6P4T part needs to be changed from COTS to Altered Item
Hydraulics |  |  | 8-32 x 1.5" shcs that hold mvvalve plate and motor plate together (through standoffs) need to be 8-32x1.625 per earlier change order
Hydraulics |  |  | titanium #4 washers?
Hydraulics
Hydraulics |  |  | #27 100221193_HexPRV_SAE4 needs to be an assembly that includes this part and the actual PRV from The Lee Company (part no:PCHR5510060S):
Hydraulics |  |  | SAE4_PRVassy
Hydraulics |  |  | 100221193_HexPRV_SAE4
Hydraulics |  |  | 5.5mmPRV_60bar_PCHR5510060S
Hydraulics |  |  | *************************
Hydraulics |  |  | 2019-02-22
Hydraulics
Hydraulics |  |  | #8 Screws through PumpMtgPlate into hex standoffs need to be .5". (eDrawing shows both .375" and .5")
Hydraulics |  |  | M5 screws through EC90MountingPlate3 into EC90 motor need to be 12mm with added flat washer (.02-.05 thick) to prevent bottoming against exposed (WTF??) circuit board on motor. (On eDrawing they are specked as 8mm)
Hydraulics |  |  | How is innerReservoirLeg mounted to endcap? Assuming set screw? 8-32 x 1"
Hydraulics
Hydraulics |  |  | 2019-02-26
Hydraulics |  |  | SHCS through oildyneStandLowerPlate are spec'd as 3/4", but should be 5/8"
Hydraulics
Hydraulics |  |  | 2019-02-27
Hydraulics |  |  | innerBellowsBulkheadClampRing holes do not match/mate with the holes in the innerBellowsMtgPlate
Hydraulics |  |  | No screws identified for this connection, either. Should be 11/16?
Hydraulics |  |  | Should this innerBellowsBulkheadClampRing be metal for the lower one? Or .375 stock thickness?
Hydraulics |  |  | holes in innerBellowsLowerBulkhead are 1/4-28 (and not tapped all the way through) and the beswick parts are 10-32
Hydraulics |  |  | It seems that pump stand legs can remain at 3" instead of the 2.75" that is specified?
Hydraulics |  |  | The NPT fittings that screw into the filter to not bury as deep as drawn.
Hydraulics |  |  | The NPT thread engagement for the 1/4NPT fitting into the filter in the drawing is different than the actual engagement
Hydraulics |  |  | -The drawing shows .219 threads showing (meaning .375 thread engagement)
Hydraulics |  |  | -The actual has and average of showing .303 showing (.3115, .2955, .2905, .3145) showing indicating a .291 thread engagement
Hydraulics
Hydraulics | GM |  | [GM] No screws specified for mounting the innerBellowsClampRings to the bulkhead parts. 8-32 button heads? Lengths? Top is 7/16? Bottom is 5/8-3/4?
Hydraulics | GM |  | [GM] Regarding innerBellowsMtgPlate: the horizontal holes that are tapped into the outer edge are correct according to the SLDDRW file, and the SLDPRT file. They are not in the correct location according to the SLDASM file. My only concern is that something else that is in the assy may be positioned incorrectly because of this (though I don’t think so...). So... make sure that the assembly drawing refers to the correct part. And if it does refer to the correct part, find out why the holes are in a different location in the assembly than they are in the part?
Hydraulics | AS |  | [AS] Need one more shell
Hydraulics | PC |  | [PC] Install shell and associated parts.
Hydraulics | PC |  | [PC] Retest/setup motorized valve operations.
Hydraulics | PC |  | [PC] tighten shaft coupler for motor/pump
Hydraulics | PC |  | [PC] drill and tap holes for wire tray mounting in innerBellowsMtgPlate and innerResUpperPlate
Hydraulics | GM | Shop | [GM, shop] Need two sheave blocks | submitted to shop
Hydraulics | GM | Shop | [GM, shop] Need two innerBellowsBulkheadClampRing-bottom
Hydraulics | GM |  | [GM] design and order parts for mounting string pot eye to innerBellowsUpperBulkhead
Elex Module | GM |  | Need all the battery pack stuff
Hydraulics | GM |  | [GM] #4 split lock washer that goes on shoulder screw for sheave block is too small. #4 ID is .120, shoulder screw is .125: M3 at .134 or #5 at .133 will work.
Hydraulics | PC |  | Need motor connectors 2X Maxon connectors ?X Twitter connectors
Hydraulics | EdM |  | Finish LHE (battery) board
Hydraulics | Gene |  | Need Twitter brackets | WO 4976
Hydraulics | Paul |  | Run hoses
Hydraulics | Gene | Mike | Alter swagelok plugs for case drain
Hydraulics | Paul |  | Order 10-32x1/8 barb fittings for pump case drain
Hydraulics | Paul |  | Install new case drain plugs
Hydraulics | Gene | SW | Motorized valve: 8-32 x 1-5/8 screws holding plates together should be reversed
Hydraulics | Gene | SW | Add more utility holes to innerBellowsMtgPlate
ELEX MODULE:
Elex Module | GM | EricM | [EM, GM] Need modified motherboard that moves large relay so board fits on elex tray. 1, 2
Elex Module | GM | Jose | Build up 2 or 3 more motherboards
Elex Module | AS |  | [AS] Bend one more elex tray.
Elex Module | PC |  | [PC] Install elex tray.
Elex Module | PC |  | [PC] Finish all elex module assembly. 1, 2
Elex Module | GM |  | [GM] Modify drawing to eliminate switch bushings from design (for next rev… low priority)
Elex Module | GM |  | [GM] Design stand to work on Elex Module while right-side-up | Submitted to shop
Elex Module | GM |  | [GM] Get Ed and Paul McGill to finalize motherboard mods | In progress
Elex Module | GM |  | [GM] Screws that mount elexTrayBracket4 (and mirror) need to be 8-32 x 5/16. 1/4" is too short.
Elex Module | GM |  | [GM] Screws that mount the spectrometerAngleMount to the spectrometerMountingPlate need to be 8-32 x 1"
Elex Module | GM |  | [GM] Delete 3x2UChannel from elex drawing
Elex Module | GM |  | [GM] Screws that mount MSC-Uchannel to elexTray need to be 8-32 x 3/8" long. 1/4" way too short.
Elex Module | GM | SW | [GM] 4-40 x 1/4" SHCS that mounts FLBottomTab to fiberlight should be 5/16"?
Elex Module | GM | SW | [GM] 4-40 x 1/2 SHCS that mount MSC that go through both boards need to be 4-40 x 3/4" (three of them)
Elex Module | GM | Aaron | Need 2nd elex module stand | WO 4978
Elex Module | GM |  | Need 3rd fiber assembly
Elex Module | GM | E-Tech | Start building wire harnesses (see next sheet)
Elex Module | EricM |  | Need all daughter cards properly configured and labeled with slot numbers
Elex Module | Chad |  | Finish DIO card
Elex Module | Chad |  | Finish Bluetooth card
Elex Module | PC |  | Lengthen slots in FLTopPlate (by ... 1/8"?)
Elex Module | PC |  | Make sure all connectors/housings/crimps are in stock (I hope)
WETTED PARTS:
Wetted Parts | GM |  | [GM¦ Get Paul the 3rd CTD (1 is on the existing CPF, 1 Paul has one an old end cap, 1 is on the old CPF proto, 1 is on the TTP and 1 is on the way)
Wetted Parts | GM |  | [GM, PC] Order/steal 4 more Subconn micro circular 8 ways | Connectors are 16 weeks out, I've got one more on the original prototype in chem sensor lab
Wetted Parts | GM |  | [GM] Get bulkhead to Seabird for new CTD
Wetted Parts | EricM |  | 2 more antennas | Eric has 1, Gene has 1 for Eric to test
Wetted Parts | GM |  | Need 2nd optode stem
Wetted Parts | GM |  | Something else we forgot
Wetted Parts | GM |  | Maybe design new OCR bracket
BUCKET BELLOWS:
Bucket Bellows | GM | Shop | Need printed parts | Parts expected by end of May, waiting for new printer
Bucket Bellows | GM |  | Rest of stuff kitted
Bucket Bellows | GM |  | Probably missing some 1/4-20 heilcoils | Can use stainless or phosphor bronze.
INTEGRATION
| Cene | Eric | Develop test plan/list
| Gene |  | Label 3X CPFs SN001, SN002 SN003
| EricM |  | Test motherboard 1 and 2
| EricM |  | Test Switch board 1, 2, 3, 4, 5, 6
| Chad |  | Test DIO board 1, 2, 3
| Chad |  | Test bluetooth board 1, 2, 3
| EdM |  | Test LHE board 1, 2
| Gene/EricM |  | Test CTD 1, 2
| Gene/EricM |  | Test Optode 1, 2
| Gene/EricM |  | Test OCR504 1, 2
| Gene/EricM |  | Test MSC/pH/Nitrate 1, 2
| Gene/EricM |  | Test FLBB 1, 2
| Gene/EricM |  | Test GPS
| Gene/EricM |  | Test Iridium
| Ed/Gene |  | Test Charger 1, 2
| Gene/EricM |  | Test motorized valve 1, 2
| Gene/EricM |  | Test position transducer 1, 2
| Gene |  | Figure out how to do a full pressure hydraulics test
| Gene/EricM |  | Pre test hydraulics 1, 2
| Gene |  | Fill with oil 1, 2
| Gene/EricM |  | Test hydraulics 1, 2
| Gene/EricM |  | Tank test 1, 2
| Gene/EricM/??? |  | Sea test 1, 2
| Gene | PW, CS | Calibrate Nitrate and pH sensors 1, 2
| Gene |  | Decide and implement external Iridium/GPS tracker and/or Homer beacon

## Wire Harnessi
Num. | Name | Top to Bottom? | Resp Engr. | Release To Mfg | Notes
1 | WH- GPS | N | Chad |  | Gene will add what's needed in the short term
2 | WH-USB | N | Gene |  | Paul will check connector p/n
3 | WH-CTD Pwr/Comms | N | Gene | Gene
4 | WH - Hydraulics | Y | Ed |  | Ed needs to check and modify as necessary
5 | WH-BluetoothConsole | N | Chad |  | Needs to be created
6 | WH-Iridium | N | Eric |  | Filtered DB25 or not?
7 | WH-FLBB | N | Gene | Gene
8 | WH-Optode | N | Gene | Gene | Needs photo of as built Lemo
9 | WH-OCR504 | N | Gene | Gene
10 | WH-On/Off | Y | Ed |  | Is this ready?
11 | WH-Charger | Y | Ed |  | Needs to be created
12 | WH-Motorized Valve | Y | Chad |  | Paul to connectorize motor and add p/n
13 | WH-Pos Xducer | Y | Chad |  | Is this ready?
14 | WH-MoBo Pwr | Y | Ed |  | Needs to be created
15 | WH-MV Halls | N | Gene |  | Moved into WH-Motorized Valve
16 | WH-MSC | N | Eric |  | Is this ready?
17 | GPS Antenna | N | Gene
18 | Iridium Antenna | N | Gene