## Sheet1
CPF Production Checkout Form
Revision 3
Unit SN:
1. Installation
2. LHE (SN: 0002)
1. 6 Batteries Installed
2. SB1-10 unconnected
3. JP1 removed for Sleep enabled
4. JP2-3 2-2 for logic control
3. Motherboard (SN: 007)
1. ☒ SD Card Inserted (Size: 16GB)
2. ☒ JP1, JP2 Removed (LED Disable)
3. ☒ JP3 MODE wired for USB MODE
4. ☒ USB client harness installed
4. Daughtercards
1. ☒ SN2 in SLOT-1 (SN: P70729)
2. ☒ SN1 in SLOT-2 (SN: P70722)
3. ☒ SN3 in SLOT-3 (SN: P70734)
4. ☒ BTB on mount: Configured for RS232, LED resistors removed,
5. (SN: 004)
6. ☒ ISB in SLOT-6 (SN: 04)
5. Upper Assembly Hardware
1. ☒ MSC/ISUS/DuraFet (SN’s: P85922, P85970)
2. ☒ SBE Board (SN: P211239)
3. ☒ GPS (SN: No mark)
4. ☒ Iridium Modem
5. (SN: 01H9B)
6. (IMEI: 300125060569270)
7. (SIM: ???)
8. ☐ GPS/Iridium subsystem deck test
6. Lower Assembly Hardware
1. ☒ String pot & ADC (SN: STR:36920, ADC: NO Mark )
2. ☒ ELMO & Motor (SN: GS2194723665)
3. ☒ Motorized Valve
4. ☐ Arrow pointing toward pump
5. ☐ Bellows Plumbed
7. Wire Harness Check
1. ☒ WH-Battery Charger
2. ☒ WH-BT Console
3. ☒ WH-CTD Pwr/Comms
4. ☒ WH-FLBB
5. ☒ WH-GPS
6. ☒ WH-Iridium Comms
7. ☒ WH-LHE to MoBo Pwer/ISB
8. ☒ WH-Mot Valve
9. ☒ WH-MSC
10. ☒ WH-Fiberlite
11. ☒ WH-OCR504
12. ☒ WH-On/Off Switches
13. ☒ WH-Optode
14. ☒ WH-Pos Xducer
15. ☒ WH-PTH
16. ☒ WH-Pump Motor
17. ☒ WH-ucComms
18. ☐ Finalize all WH routings
8. Pre-oil Fill
1. ☒ Motherboard SW Checkout
2. ☒ Energy Monitor BATT
3. ☒ 12V Control
4. ☒ 5V Control
9. Sensor Functionality
1. ☒ SLOT1-J5 to SLOT5 BT Console PWR/TELEM
2. ☒ SLOT1-J2 CTD PWR/TELEM
3. ☒ SLOT1-J4 Pump PWR/TELEM
4. ☒ SLOT2-J2-J3 Iridium PWR/TELEM
5. ☒ SLOT2-J4 MSC PWR/TELEM
6. ☒ SLOT2-J5 Optode PWR/TELEM (SN: 2707)
7. ☒ SLOT3-J4 OCR PWR/TELEM (SN: )
8. ☒ SLOT3-J5 FLBB PWR/TELEM (SN: )
9. ☒ SLOT6-J1 GPS PWR/TELEM (SN: )
10. ☒ SLOT6-J2 Bellows Position PWR/TELEM
11. ☒ SLOT3-J6 Mot Valve PWR/DIO (SN: )
12. ☒ SLOT6-J8 LHE I2C Attached
10. LHE
1. ☒ LHE Battery Polling
2. ☒ LHE Sleep Test
3. ☒ LHE Pump PWR/TELEM
1. ☒ Verify 2048 counts/rev
4. ☒ LHE Pump Energy Monitor
5. ☒ Charging Cycle through Endcap
11. Calibrations
1. ☒ MSC Calibrations
2. ☒ Environmental Sensors on ISB
12. Closed Unit Deck Test
1. ☐ Iridium Deck Test
2. ☐ GPS Deck Test
3. ☒ Bluetooth Deck Test
13. Fill with oil when 1-12 are complete
14. String Pot Cal
1. 0% Full (bellows upper plate against bellows bottom
1. ADC counts =
2. Voltage =
2. 100% Full (bellows upper plate 3mm below fixed top plate
1. ADC counts =
2. Voltage =
3. Slope = Inter. =
15. Fill With Oil |  | 2021-04-20 | 2021-04-22
1. Total oil in GC to start = millLiters |  | 1050 | 1550
2. Left in GC at end = |  | 300 | 575
3. Oil in CPF (a – b) = |  | 750 | 975
4. Total Oil fill | 1725
16. Benchtop
1. ☐ Pump/Motor Calibration
2. ☐ Pump Bellows Cycling (10x)
3. ☐ Install desiccant packs
4. ☐ Close Unit
Tank Tests
17. Surface Operations
1. ☐ Bluetooth
2. ☐ Temperature & Humidity Good (<25%RH)
3. ☐ GPS [ATTEMPT]
4. ☐ IRIDIUM SBD [ATTEMPT]
5. ☐ IRIDIUM SBD [ATTEMPT]
18. Buoyancy Operations
1. ☐ Ballast Tests
2. ☐ SurfaceOps Bellows Position
3. ☐ Descent/Ascent
4. ☐ Velocity Control
5. ☐ Depth Holding
6. ☐ Profile Control
7. ☐ Sampling Profile
19. Configuration File Options
1. TBD
GENERAL COMMENTS: