## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | BSC approval | 10 days | May 11, 2021 8:00 AM | May 24, 2021 5:00 PM |  | 1
2 | Yes | Auto Scheduled | overall mechanical | 10 days | May 11, 2021 8:00 AM | May 24, 2021 5:00 PM |  | 2
3 | Yes | Auto Scheduled | 2mm radial spacing | 10 days | May 11, 2021 8:00 AM | May 24, 2021 5:00 PM |  | 2
4 | Yes | Auto Scheduled | BQ76942 BMS | 10 days | May 11, 2021 8:00 AM | May 24, 2021 5:00 PM |  | 2
5 | Yes | Auto Scheduled | 4P no inter-cell fusing | 10 days | May 11, 2021 8:00 AM | May 24, 2021 5:00 PM |  | 2
6 | Yes | Auto Scheduled | CPF System Engineering | 1 day | May 11, 2021 8:00 AM | May 11, 2021 5:00 PM |  | 1
7 | Yes | Manually Scheduled | FMEA |  |  |  |  | 2
8 | Yes | Auto Scheduled | BMS | 120 days | May 11, 2021 8:00 AM | October 25, 2021 5:00 PM |  | 1
9 | Yes | Auto Scheduled | CCA | 60 days | August 3, 2021 8:00 AM | October 25, 2021 5:00 PM |  | 2
10 | Yes | Auto Scheduled | Design | 20 days | August 3, 2021 8:00 AM | August 30, 2021 5:00 PM | 21 | 3
11 | Yes | Auto Scheduled | Review | 5 days | August 31, 2021 8:00 AM | September 6, 2021 5:00 PM | 10,1 | 3
12 | Yes | Auto Scheduled | Build | 15 days | September 7, 2021 8:00 AM | September 27, 2021 5:00 PM | 11 | 3
13 | Yes | Auto Scheduled | Test | 20 days | September 28, 2021 8:00 AM | October 25, 2021 5:00 PM | 12 | 3
14 | Yes | Auto Scheduled | Define register settings | 10 days | May 11, 2021 8:00 AM | May 24, 2021 5:00 PM |  | 2
15 | Yes | Auto Scheduled | Eval board testing | 15 days | May 11, 2021 8:00 AM | May 31, 2021 5:00 PM |  | 2
16 | Yes | Auto Scheduled | LHE-HDBP | 60 days? | May 11, 2021 8:00 AM | August 2, 2021 5:00 PM |  | 1
17 | Yes | Manually Scheduled | Finalize Motor selection |  |  |  |  | 2
18 | Yes | Auto Scheduled | Design | 20 days | May 11, 2021 8:00 AM | June 7, 2021 5:00 PM |  | 2
19 | Yes | Auto Scheduled | Review | 5 days | June 8, 2021 8:00 AM | June 14, 2021 5:00 PM | 18 | 2
20 | Yes | Auto Scheduled | Build | 15 days | June 15, 2021 8:00 AM | July 5, 2021 5:00 PM | 19,1 | 2
21 | Yes | Auto Scheduled | Test | 20 days | July 6, 2021 8:00 AM | August 2, 2021 5:00 PM | 20 | 2
22 | Yes | Auto Scheduled | Charger | 70 days? | October 26, 2021 8:00 AM | January 31, 2022 5:00 PM |  | 1
23 | Yes | Manually Scheduled | Prototype new/risky elements (I2C driver, Labview to BQ76942 comms, NI USB to I2C module) |  |  |  |  | 2
24 | Yes | Auto Scheduled | Design | 30 days | October 26, 2021 8:00 AM | December 6, 2021 5:00 PM |  | 2
25 | Yes | Manually Scheduled | Electrical | 20 days | October 26, 2021 8:00 AM | November 22, 2021 5:00 PM | 8 | 3
26 | Yes | Manually Scheduled | Labview VI | 30 days | October 26, 2021 8:00 AM | December 6, 2021 5:00 PM | 8 | 3
27 | Yes | Auto Scheduled | Review | 5 days | December 7, 2021 8:00 AM | December 13, 2021 5:00 PM | 24,1 | 2
28 | Yes | Auto Scheduled | Build | 15 days | December 14, 2021 8:00 AM | January 3, 2022 5:00 PM | 27 | 2
29 | Yes | Auto Scheduled | Test | 20 days | January 4, 2022 8:00 AM | January 31, 2022 5:00 PM | 28 | 2
30 | Yes | Auto Scheduled | Embedded Software | 1 day? | May 11, 2021 8:00 AM | May 11, 2021 5:00 PM | 24 | 1
31 | Yes | Manually Scheduled | BQ76942 Unit test |  |  |  |  | 2
32 | Yes | Auto Scheduled | Mechanical | 1 day? | May 11, 2021 8:00 AM | May 11, 2021 5:00 PM |  | 1
33 | Yes | Manually Scheduled | Thermal mock up |  |  |  |  | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | BSC | B | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Ed | E | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Chad | C | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Gene | G | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Eric | E | Work |  |  |  |  | 100% | $0.00/h | 0
6 | all | a | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
BSC approval | BSC | 0 | 80h | 100%
FMEA | Gene | 0 | 8h | 100%
FMEA | all | 0 | 8h | 100%
BMS | Ed | 0 | 960h | 100%
BMS | Chad | 0 | 960h | 100%
LHE-HDBP | Ed | 0 | 480h | 100%
Charger | Ed | 0 | 560h | 100%
Charger | Gene | 0 | 560h | 100%
Embedded Software | Eric | 0 | 8h | 100%
Embedded Software | Gene | 0 | 8h | 100%