## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Fixed Costs | Outline Level | Notes
1 | Yes | Auto Scheduled | Project Start | 0 days | December 1, 2023 8:00 AM | December 1, 2023 8:00 AM |  |  | 1
2 | Yes | Auto Scheduled | Engineering | 3 days? | December 1, 2023 8:00 AM | December 5, 2023 5:00 PM |  |  | 1
3 | Yes | Auto Scheduled | Finalize System Architecture | 3 days? | December 1, 2023 8:00 AM | December 5, 2023 5:00 PM |  |  | 2
4 | [8 empty] | 2
5 | Yes | Auto Scheduled | SL1 subsystem | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 2
6 | Yes | Auto Scheduled | Finalize SL1 Design | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 3
7 | Yes | Auto Scheduled | CPF Interface | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 3
8 | Yes | Auto Scheduled | Design | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 4
9 | Yes | Auto Scheduled | Build | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 4
10 | Yes | Auto Scheduled | Test | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 4
11 | Yes | Auto Scheduled | Build first article | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 2
12 | [8 empty] | 2
13 | Yes | Auto Scheduled | CPF Subsystem | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 2
14 | Yes | Auto Scheduled | SL1 Bracketry | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 3
15 | Yes | Auto Scheduled | Build first article | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 3
16 | [8 empty] | 3
17 | Yes | Auto Scheduled | System Integration | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 2
18 | Yes | Auto Scheduled | Integrate first article (at MBARI?) | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 3
19 | Yes | Auto Scheduled | Tank Test | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 3
20 | [8 empty] | 3
21 | Yes | Auto Scheduled | Science | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 1
22 | Yes | Auto Scheduled | Develop science plan | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 2
23 | Yes | Auto Scheduled | Data plan | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 3
24 | Yes | Auto Scheduled | Experiment plan | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 3
25 | [8 empty] | 3
26 | Yes | Auto Scheduled | Field work | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 1
27 | Yes | Auto Scheduled | Experiment 1 | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 2
28 | Yes | Auto Scheduled | Experiment 2 | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 2
29 | Yes | Auto Scheduled | Experiment 3 | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 2
30 | [8 empty] | 2
31 | Yes | Auto Scheduled | Project Management | 188 days? | December 1, 2023 8:00 AM | August 20, 2024 5:00 PM |  |  | 1
32 | Yes | Auto Scheduled | Management | 1 day? | December 1, 2023 8:00 AM | December 1, 2023 5:00 PM |  |  | 2
33 | Yes | Auto Scheduled | Transition Plan | 80 days? | May 1, 2024 8:00 AM | August 20, 2024 5:00 PM |  |  | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Fixed Costs | Max Units | Standard Rate | Cost Per Use | Notes
1 | Gene | G | Work | [5 empty] | 100% | $0.00/h | 0
2 | Michael | M | Work | [5 empty] | 100% | $0.00/h | 0
3 | Gene Michael | G | Work | [5 empty] | 100% | $0.00/h | 0
4 | Yi | Y | Work | [5 empty] | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units | Fixed Costs
Finalize System Architecture | Gene | 0 | 1.5d | 50%
Finalize System Architecture | Michael | 0 | 1.5d | 50%
Transition Plan | Gene | 0 | 8d | 10%
Transition Plan | Yi | 0 | 8d | 10%