## Sheet1
2020 Project Start Date: | Experiment 1 | Experiment 2 | Inertial Current Meter | High Energy Density Pack Design scoping only | Commercialization Plan | Total Resources[1] (in hours) for each resource category for all milestones listed here
Milestone Date | 2020-09-01 | 2020-11-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
Milestone Description
Electrical Engineer | 250 | 250 | 150 | 100 |  | 1250
Software Eng-Embedded
Software Eng-Info Eng
Mechanical Engineer
Mechanical Eng-Division
Mechanical Eng-Mfg
Associate Engineer | 120 | 120 |  |  |  | 240
Electrical Tech | 190 | 190 |  | 40 |  | 420
Software Tech
Mechanical Tech | 160 | 160 |  |  |  | 320
Machinist | 80 | 80 |  | 40 |  | 200
Divers