## Task_Table1
Outline Number | Task Name | Duration | Work | Start | Finish | % Complete | Notes | Predecessors | Resource Names
1 | eTech Tasks | 42 days? | 45 days | Thu 8/22/19 | Fri 10/18/19 | 0%
1.1 | Build 3rd LHE | 19 days | 4 days | Tue 9/24/19 | Fri 10/18/19 | 0% |  | 14 | Jose
1.2 | Build 3rd ISB | 16 days | 3 days | Fri 8/30/19 | Fri 9/20/19 | 0% |  | 21 | Jose
1.3 | Ed's wire harnesses | 22 days? | 3 days | Thu 8/22/19 | Fri 9/20/19 | 0% |  |  | Jose
1.4 | Chad's wire harnesses | 22 days? | 3 days | Thu 8/22/19 | Fri 9/20/19 | 0% |  |  | Jose
1.5 | Build 4th and 5th LHE | 2 days | 8 days | Mon 9/30/19 | Tue 10/1/19 | 0% | Jose to provide real date | 15 | Jose
1.6 | Build 4th and 5th ISB | 6 days | 6 days | Tue 10/1/19 | Tue 10/8/19 | 0% | Jose to decide build in or out and provide a date | 24 | Jose
1.7 | Build 6th motherboard | 3 days | 3 days | Wed 10/9/19 | Fri 10/11/19 | 0% | Need to find extra boards | 6,7 | Jose
1.8 | First BT board | 5 days | 5 days | Mon 9/23/19 | Fri 9/27/19 | 0% |  | 3,4,5 | Jose
1.9 | 2-5 BT boards | 10 days | 10 days | Mon 9/30/19 | Fri 10/11/19 | 0% |  | 9 | Jose
1.1 |  | 1 day? | 0 days | Tue 8/20/19 | Tue 8/20/19 | 0%
2 | Finish LHE CCA | 46.67 days? | 29.8 days | Tue 8/20/19 | Wed 10/23/19 | 0%
2.1 | Ed's bench testing | 21 days | 16.8 days | Tue 8/20/19 | Tue 9/17/19 | 0% |  |  | Ed[80%]
2.2 | Eric's software testing | 4 days | 2 days | Wed 9/18/19 | Mon 9/23/19 | 0% |  | 13 | Eric[50%]
2.3 | Integrate and test in SN002 | 4 days | 4 days | Tue 9/24/19 | Fri 9/27/19 | 0% | reevalute integrating (or not) prototype | 14,4,13 | Ed[50%],Eric[50%]
2.4 | Integrate and test in SN003 | 3 days | 3 days | Mon 9/30/19 | Wed 10/2/19 | 0% | reevalute integrating in series or parallel | 15,4 | Ed[50%],Eric[50%]
2.5 | Integrate and test in SN001 | 2.67 days? | 4 days | Mon 10/21/19 | Wed 10/23/19 | 0% |  | 2,16 | Ed[50%],Eric[50%],Gene
3 |  | 1 day? | 0 days | Tue 8/20/19 | Tue 8/20/19 | 0%
4 | Finish ISB CCA | 30 days? | 10 days | Tue 8/20/19 | Mon 9/30/19 | 0%
4.1 | Chad's bench testing | 4 days | 2 days | Tue 8/20/19 | Fri 8/23/19 | 0% | 1 and 2 done |  | Chad[50%]
4.2 | Eric's software testing | 4 days? | 2 days | Mon 8/26/19 | Thu 8/29/19 | 0% | 1 and 2 done | 20 | Eric[50%]
4.3 | Integrate and test in SN002 | 2 days | 2 days | Mon 9/23/19 | Tue 9/24/19 | 0% | Chad to check on harnesses | 21,20,5 | Chad[50%],Eric[50%]
4.4 | Integrate and test in SN003 | 2 days? | 2 days | Wed 9/25/19 | Thu 9/26/19 | 0% |  | 22,5 | Chad[50%],Eric[50%]
4.5 | Integrate and test in SN001 | 2 days? | 2 days | Fri 9/27/19 | Mon 9/30/19 | 0% |  | 3,23 | Chad[50%],Eric[50%]
4.6 |  | 1 day? | 0 days | Tue 8/20/19 | Tue 8/20/19 | 0%
5 | Finish BT CCA | 34 days? | 8 days | Tue 8/20/19 | Fri 10/4/19 | 4%
5.1 | Finish Design | 1 day | 1 day | Tue 8/20/19 | Tue 8/20/19 | 100% |  |  | Chad
5.2 | Layout | 9 days | 0 days | Thu 9/5/19 | Tue 9/17/19 | 0% |  | 27
5.3 | Build CCA | 5 days | 0 days | Wed 9/18/19 | Tue 9/24/19 | 0% |  | 28
5.4 | Chad's bench testing | 2 days | 1 day | Wed 9/25/19 | Thu 9/26/19 | 0% |  | 29 | Chad[50%]
5.5 | Eric's software testing | 2 days | 1 day | Fri 9/27/19 | Mon 9/30/19 | 0% |  | 30 | Eric[50%]
5.6 | Wire Harness Drawing | 1 day? | 1 day | Tue 8/20/19 | Tue 8/20/19 | 0% |  |  | Chad
5.7 | Integrate and test in SN002 | 2 days | 2 days | Tue 10/1/19 | Wed 10/2/19 | 0% |  | 31 | Chad[50%],Eric[50%]
5.8 | Integrate and test in SN003 | 1 day? | 1 day | Thu 10/3/19 | Thu 10/3/19 | 0% |  | 33 | Chad[50%],Eric[50%]
5.9 | Integrate and test in SN001 | 1 day? | 1 day | Fri 10/4/19 | Fri 10/4/19 | 0% |  | 34 | Chad[50%],Eric[50%]
5.1 |  | 1 day? | 0 days | Tue 8/20/19 | Tue 8/20/19 | 0%
6 | Finish shore side Iridium testing | 6 days? | 3 days | Tue 8/20/19 | Tue 8/27/19 | 0% |  |  | Eric[50%]
7 |  | 1 day? | 0 days | Tue 8/20/19 | Tue 8/20/19 | 0%
8 | Finish Building SN002 | 2 days? | 2 days | Mon 9/30/19 | Tue 10/1/19 | 0% |  | 22,15 | Paul
9 | Finish Building SN003 | 2 days? | 2 days | Thu 10/3/19 | Fri 10/4/19 | 0% |  | 23,16 | Paul
10 |  | 1 day? | 0 days | Tue 8/20/19 | Tue 8/20/19 | 0%
11 | Bench Test SN002 | 3 days | 6 days | Wed 10/2/19 | Fri 10/4/19 | 0% |  | 22,15,39 | Gene,Eric
12 | Bench Test SN003 | 3 days? | 6 days | Mon 10/7/19 | Wed 10/9/19 | 0% |  | 16,23,40 | Gene,Eric
13 | Bench test SN001 | 3 days? | 6 days | Wed 10/23/19 | Mon 10/28/19 | 0% |  | 17,24 | Gene,Eric
14 |  | 1 day? | 0 days | Tue 8/20/19 | Tue 8/20/19 | 0%
15 | Tank Test SN001 | 2 days | 2 days | Mon 10/28/19 | Wed 10/30/19 | 0% |  | 44 | Gene
16 | Tank Test SN002 | 2 days | 2 days | Mon 10/7/19 | Tue 10/8/19 | 0% |  | 42 | Gene
17 | Tank Test SN003 | 2 days | 2 days | Thu 10/10/19 | Fri 10/11/19 | 0% |  | 43 | Gene
18 |  | 1 day? | 0 days | Tue 8/20/19 | Tue 8/20/19 | 0%
19 | Sea Test SN001 | 6 days | 3 days | Wed 10/30/19 | Thu 11/7/19 | 0% |  | 46 | Gene[50%]
20 | Sea Test SN002 | 6 days | 3 days | Thu 11/7/19 | Fri 11/15/19 | 0% |  | 47,50 | Gene[50%]
21 | Sea Test SN003 | 6 days | 3 days | Fri 11/15/19 | Mon 11/25/19 | 0% |  | 48,51 | Gene[50%]
22 |  | 1 day? | 0 days | Tue 8/20/19 | Tue 8/20/19 | 0%
23 | Finish Operational Software | 20 days? | 20 days | Tue 8/20/19 | Mon 9/16/19 | 0% |  |  | Gene Eric
24 |  | 1 day? | 0 days | Tue 8/20/19 | Tue 8/20/19 | 0%
25 | Pre-run Science mission | 0 days | 0 days | Mon 11/25/19 | Mon 11/25/19 | 0% |  | 52,50,51 | Gene,Eric