## Sheet1
WBS | Task Name | Duration | Work | Resource Names | Cost | Fixed Cost | Notes (P1 = highest priority, P5 = lowest priority)
1 | System Engineering | 49 days? | 35 days |  | 0 | 0
1.1 | Refine submerge, anchor and de-anchor algorithms | 10 days? | 10 days | Gene Massion | 0 | 0 | MBARI project
1.2 | Refine depth control algorithm | 25 days? | 25 days | Gene Massion | 0 | 0 | MBARI project
2 | Software Development | 385 days? | 186 days |  | 132000 | 0
2.1 | Refactor code | 185 days? | 131 days |  | 100000 | 0 | P1
2.1.1 | design | 10 days | 25 days |  | 20000 | 0
2.1.1.1 | Gene | 10 days | 10 days | Gene Massion | 0 | 0
2.1.1.2 | Eric | 5 days | 5 days | Eric Martin | 0 | 0
2.1.1.3 | Dan | 10 days | 10 days | Dan Smith | 20000 | 0
2.1.2 | write code, test, repeat | 150 days? | 75 days | New Hire[50%] | 60000 | 0
2.1.3 | Develop comprehensive unit and module test framework | 185 days? | 31 days |  | 20000 | 0 | P1
2.1.3.1 | Eric | 6 days? | 6 days | Eric Martin | 0 | 0
2.1.3.2 | new SW Hire | 100 days? | 20 days | New Hire[20%] | 16000 | 0
2.1.3.3 | Fully integrate benchtop simulator into test process | 25 days? | 5 days | New Hire[20%] | 4000 | 0
2.2 | Implement sleep mode | 10 days? | 10 days | Eric Martin | 0 | 0 | P1
2.3 | Validate new sensor integration process | 5 days? | 5 days | Eric Martin | 0 | 0 | P3
2.4 | Develop under ice algorithms | 1 day? | 0 days |  | 0 | 0 | P5
2.5 | Develop new mission planner | 200 days? | 40 days | New Hire[20%] | 32000 | 0 | P2?
3 | Electrical Engr | 15 days? | 59 days |  | 22500 | 0
3.1 | Integrate production IMU | 10 days? | 20 days |  | 6000 | 6000 | P1.5
3.1.1 | Gene | 10 days? | 10 days | Gene Massion | 0 | 0
3.1.2 | Jose | 5 days? | 5 days | Jose Rosal | 0 | 0
3.1.3 | eTech | 5 days? | 5 days | ETech | 0 | 0
3.2 | Design, build, test new SOM | 10 days? | 14 days |  | 4000 | 4000 | P1.5
3.2.1 | Gene | 10 days? | 10 days | Gene Massion | 0 | 0
3.2.2 | Scott | 4 days? | 4 days | Scott Jensen | 0 | 0
3.3 | Mod, build, test motherboard as necessary | 5 days? | 10 days |  | 5000 | 5000 | P1.5
3.3.1 | Gene | 5 days? | 5 days | Gene Massion | 0 | 0
3.3.2 | Scott | 5 days? | 5 days | Scott Jensen | 0 | 0
3.4 | Design, build, test new motor controller | 15 days? | 15 days |  | 7500 | 7500 | P2.5
3.4.1 | Scott | 15 days? | 15 days | Scott Jensen | 0 | 0
4 | Mechanical Engineering | 225 days? | 80 days |  | 99600 | 0
4.1 | Drawing check | 100 days? | 20 days | Mark Greise[20%] | 22400 | 0 | P1
4.2 | Design new housing | 150 days? | 30 days | Mark Greise[20%] | 33600 | 0 | P3
4.3 | Update test tank prototype drawings | 75 days? | 15 days | Mark Greise[20%] | 16800 | 0 | P1
4.4 | New GPS antennas | 75 days? | 15 days | Mark Greise[20%] | 26800 | 10000 | P2
5 | Test | 1000 days? | 160 days |  | 128000 | 0
5.1 | Continuous tank testing | 1000 days? | 100 days | New Hire[10%] | 80000 | 0 | P1
5.2 | At sea engineering tests |  | 60 days | New Hire[20%] | 48000 | 0 | P1
6 | Science Missions | 1 day? | 0 days |  | 0 | 0
6.1 | Science missions Year 1 | 1 day? | 0 days |  | 0 | 0 | MBARI project
6.2 | Science missions Year 2 | 1 day? | 0 days |  | 0 | 0 | MBARI project
6.3 | Science missions Year 3 | 1 day? | 0 days |  | 0 | 0 | MBARI project
7 | Production | 125 days? | 0 days |  | 172000 | 0
7.1 | Update test tank prototype | 50 days | 0 days |  | 12000 | 12000 | P1
7.2 | Build SN004 and SN005 | 1 day? | 0 days |  | 160000 | 160000 | P5
8 | Technology transfer | 49 days? | 22 days |  | 0 | 0
8.1 | Develop and conduct potential users survey | 25 days? | 10 days | Gene Massion[20%],Yui Takeshita[33%] | 0 | 0 | P3
8.2 | Develop TT strategy | 24 days? | 12 days | Gene Massion[25%],Yui Takeshita[25%] | 0 | 0 | P5
9 | Materials | 780 days | 0 days |  | 22500 | 0
9.1 | Year 1 | 260 days | 0 days |  | 7500 | 7500 | up for discussion
9.2 | Year 2 | 260 days | 0 days |  | 10000 | 10000 | up for discussion
9.3 | Year 3 | 260 days | 0 days |  | 5000 | 5000 | up for discussion