## Sheet1
Critical Path | Main Task | Detailed task | Status |  | Responsible
Design, build test here
|  | Get PCBs and pins | Done |  | Gene
* |  | Finish ESD safe bonding fixture. | The non-ESD safe fixture is printed and looks like it will work | I'll put the work order in for the ESD safe fixture today or tormorrow | Gene
|  |  | Jim is building a few PCBs |  | Jim
|  |  | Once I make sure those PCBs work, we'll print the ESD safe fixture and build a few more PCBs | Should be done mid next week | Gene
Bonding
* |  | Static safe working area and tools and Chip holders | ? | Needs to be done mid next week | Luke
* |  | Assemble real ISFETs in bonding fixture | Need the ESD safe fixture, working area, tools and chip holders | 2023-08-03 | Gene
* |  | Bonding in San Jose |  | 2023-08-08 | Gene
Build and test new GDFlionix
* |  | Machine housing, back cover plate, ISFET spacer | Mark is working on these | Hopefully Aug 10 | Shop
* |  | Build up a GDFl |  |  | Gene, Peter, Ben
* |  | Test plan |  |  | Ken, Yui
* |  | Test |  |  | Peter, Ben