## Sheet1
GDF To Do List
Date | Number | GDF Tests | Stuckee | Due Date | Notes
2022 Nov 17 | 1 | Build up a GDF with Prunella parts and a “bad” ISFET | Peter, Ben
2022 Nov 17 | 2 | Redo the GDF with O-ring cover plate test | Peter, Ben |  | All current parts (no broached housing)
2022 Nov 17 | 3 | Put a “bad” ISFET in a DSD | Peter, Ben
2022 Nov 17 | 4 | Think about tests to help understand the weird GDF f(p) | All
2022 Nov 17 | 5 | Redesign the DSD to take a gasket | Gene
Action items
2022 Nov 17 | 1 | Look at redesigning either GDFVer1 or GDFVer2 to take the Honeywell ISFET | Gene
2022 Nov 17 | 2 | Decide which flow hood to install on go-to-sea GDFs | Ken, Yui
Lionix To Do List
2022 Nov 17 | 1 | Finalize pad stackup and size | Ken, Luke |  | Ask Lionix if they have bonded gold wire to gold over aluminum pad
2022 Nov 17 | 2 | Build Lionix simulated chip with gold wire for manufacturability test | Gene