D-ESP 800237 INTEGRATION & TEST SCHEDULE
INTEGRATION:

Mechanical: (MG, MB, MP)
1. DPU Unit [October 17-28]
a. Fabrication (MB)

b. Assembly (MP)

2. Sampler Unit [October 17-28]
a. Design = electronics chassis (MG)

b. Fabrication

c. Assembly (MP)

3. Hydraulics Housing [October 17-28]
a. Design = electronics chassis (MP)

b. Fabrication (MB)

c. Assembly (MP)

4. Electrical Housing [October 17-28]
a. Fabrication (MG)

b. Assembly (MP)

Electrical:   (SJ, CE, JR)
1. Electrical Design  [October 17-28]  (SJ)
a. Design (SJ, CE)
b. Drawing entry (CE)
c. Cables (CE)
2. DPU Unit  [October 17-28]  (JR, CE)
a. Wiring/Assembly (JR, CE)
3. Hydraulic Housing  [October 17-28]  (JR, CE)
a. Wiring/Assembly (JR, CE)
4. Sampler Unit  [October 17-28]  (JR, CE)
a. Wiring/Assembly (JR, CE)
5. Electrical Housing [October 17-28]   (JR, CE)
a. Wiring/Assembly (JR, CE)
TEST:

Sub-system Testing:  (JR, CE)
1. Servo test [November 14-18] (JR, CE)
a. Tuning (JR, CE)
2. Valve test  [November  14-18] (JR, CE)
a. Tuning (JR, CE)
3. Pressure test [November 1-4] (MB, MP)
a. Test procedures (MB)

b. DPU (MB, MP)
c. Sampler (MB, MP)
d. D-ESP Housing (MB, MP)
e. Electronics housing (MB, MP)
f. Hydraulics housing (MB, MP)
4. DPU & Sampler (JR, CE)
a. Test procedures (SJ, MB)

b. Actuation (JR, CE)
c. Synchronization (JR, CE)
System Testing:  [November 21-25] (JR, CE, SJ, MB, MP)
1. Test procedures (SJ, CS)

Depressurization & Sampling (JR, CE, SJ, MB, MP)
Component order:  [October 3-7] (CE)
1. Electrical/mechanical (JR, CE)
2. Bill of Materials (SJ, MB)
