4k Deep ESP Test Plan

v0.01
Testing of 4k DWSM system to be mostly completed on shore. 

In Ocean testing
Purpose of sea testing is to demonstrate elevator deployment and recovery, and verify complete system operation and readiness for Axial deployment.

Primary goals:

1. Demonstrate elevator deployment, descent, landing, release, ascent, surface expression, locating and recovery.

2. Demonstrate elevator relocation, sniffer wand deployment and positioning.

3. Demonstrate wet-mate communications and powering of system, acoustic communications and recall, full process cycle, intake, decompress, feed (to dummy core?), repressurize, exhaust, clean.
4. Demonstrate ISUS, CTD monitoring of sample point while and whilst not intaking and exhausting

5. Demonstrate error condition and recovery, including:
a. Bag squeeze, burst

b. Gas generation, pass, venting, and completion of cycle

6. Take baseline data of:

a. Power consumption

b. Descent, ascent rates.

c. Process time

7. Complete mission with ESP core, 
a. SHA

b. PCR

c. Record consumables, including power.
Dive 1: (Mar 25) 

1. Deploy Elevator in full weight mode, without core, at depth capability of Ventana.

2. Relocate elevator, deploy/position sniffer wand

3. Wetmate connection to “helper brain”
4. Operate DWSM and process thru dummy core. 

5. Test error conditions

6. De-mate

7. Manual release of elevator. 

8. Recover drop weight.

9. Ship recovery of elevator.

Dive 2: (April 7)
1. Deploy Elevator in full weight mode, with core (+/- MFB) sniffer wand, CTD, and ISUS. (may need to use 1000m ISUS if 4000m ISUS is not available.)

2. Relocate elevator, deploy/position sniffer wand

3. Wetmate comms and power. 

4. Operate Deep ESP, small (1L) process and large (10L HV) process as time allows, short WCRs only (no chemistry)
5. De-mate

6. Acoustic modem communications

7. Acoustic recall of elevator

8. Recover drop weight.

9. Ship recovery of elevator.

Dive 3: (April 14)
1. Deploy Elevator in full weight mode, with core (+/- MFB) sniffer wand, CTD, and ISUS. (may need to use 1000m ISUS if 4000m ISUS is not available.)

2. Relocate elevator, deploy/position sniffer wand

3. Wetmate comms and power. 

4. Initiate Deep ESP, small (1L) process and large (10L HV) process as time allows. 
5. Wetmate to elevator, check status, download data.
6. De-mate from elevator

7. Acoustic recall of elevator

8. Recover drop weight.

9. Ship recovery of elevator.

Dive 4: Deploy DESP (May 4, up to 2 weeks, on MARS maybe)
1. Deploy Elevator in full weight mode, with core (+/- MFB) sniffer wand, CTD, and 4000m ISUS. 

2. Relocate elevator, deploy/position sniffer wand

3. Wetmate comms and power. 

4. Initiate Deep ESP mission.

5. De-mate from elevator, acoustically monitor DESP
6. Acoustic modem communications

7. Leave D-ESP to run mission

Dive 5: Recover DESP (May nte 3rd week) 
1. Locate pre-deployed DESP

2. Wetmate to elevator, check status, download data.

3. Run final stuff

4. De-mate from elevator

5. Acoustic recall of elevator

6. Recover drop weight.

7. Ship recovery of elevator.

