ESP Weekly Meeting 

01Mar07
Attending:

Doug Pargett, Scott Jensen, Chris Scholin, Brent Roman, Chris Preston





Next milestones: 
· D-ESP Deployment, Mar 5-7
· Surface ESP, April 16 - May 7 (23 days, GG, Surface Mooring, CTD)

· Surface ESP, May 17 - June 12 (28 days, GG, Surface Mooring, CTD, ISUS)

· August XX (option):
D-ESP (DWSM, A1, Deep CTD, ISUS)
· Networked Surface ESP, Aug 30 – Sept 27 (GG, A1, 2 Moorings, ISUS, CTD)

Schedule:
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1. All focus still on D-ESP. It’s into its PDV test now. Mob is tomorrow morning (Scott time) After today’s positive, do a rinse with RO water.

2. Pre-Canning images on tornado 
\\Tornado\projectlibrary\ESP\ESP Deployments\D-ESP March 07\Pre-can images
3. 12-hr dive days on March 5 & 6, 10-hr dive on Mar 7. All days early start, be onboard at 5:30 am for 6:00 am departure. 
Jensen on shore; Pargett, Roman, Scholin, Preston at sea.
Day 1: Sample at 20-40m, 500m
Day 2: Sample at 1000m, O2 min (750m)
Day 3: Sample at 200m, 1000m (if time allows)

4. Ask about popping Niskins then going deep. We’ll go with whatever they can allow.
5. Henry Bortman from Astrobiology magazine was here Feb 27. Planning to go on Mar 6th cruise.
6. Addie available March 16th or 19th. Need to arrange interviewers (Pargett, Jensen, Roman, McGill, Kirkwood, Birch, Au, etc.) 

7. Pargett to present ESP project status to Engineering meeting on March 8.

8. Charge 800560 for build solenoid driver (for bulkhead valve power reduction)
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		19-Feb		20-Feb		21-Feb		22-Feb		23-Feb

		Holiday						FSW test		Raw Water Test x2 (rinse, pickle)

		26-Feb		27-Feb		28-Feb		1-Mar		2-Mar

				Load pucks, reagents		Can, sled,		PDV (test tank)		MOB, ROV test

		5-Mar		6-Mar		7-Mar		8-Mar		9-Mar

		D-ESP Dive 1		D-ESP Dive 2		D-ESP Dive 3






