ESP Weekly Meeting 

12Apr07
Attending:

Doug Pargett, Chris Scholin, Cheri Everlove, Brent Roman, Scott Jensen





Next milestones: 
· Surface ESP, April 16 - May 7 (23 days, GG, Surface Mooring, CTD)

· Surface ESP, May 17 - June 12 (28 days, GG, Surface Mooring, CTD, ISUS)

· Deep ESP,  August 6,7 (1kDWSM, Neo, Deep CTD, ISUS)
· Networked Surface ESP, Aug 30 – Sept 27 (GG, A1, 2 Moorings, ISUS, CTD)

Schedule:
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Short Meeting:
1. Preparing of the upcoming deployment, prepping for He leak test; need to do weight check, and purge with N2.

2. QC run this afternoon

3. Anchor and rigging box to Zepher this afternoon.

4. This is a full capacity load of the instrument. (132 pucks)

5. Test of radio (shore vs backpack radio) today

6. Brent will fire it off from MBARI.

New Items:

1. Neo is here! 

2. Need an instrument log.
3. Scholin trying to get some of Joe Jones time to review scripts on Neo. 

4. Will need to determine how Neo will sample thru 1kDWSM.
5. Drifter design for C-MORE potential use.

6. Need to have a GUI meeting after GG’s in the water.

7. LLNL wants a date for the CDR.

8. PCR unit talks, but we need to build a driver.

9. A full ASTEP project meeting should be held, target is June (after the surface deployments).
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		4-Mar		5-Mar		6-Mar		7-Mar		8-Mar		9-Mar		10-Mar				Mar 12 -16

																		GG onto surface lid, Check Mooring Gear, Test DA

		11-Mar		12-Mar		13-Mar		14-Mar		15-Mar		16-Mar		17-Mar				Mar 19 - 23

												GG un-lid, Test tank new housing						Chris, Joe? Run new piezo arrays,

		18-Mar		19-Mar		20-Mar		21-Mar		22-Mar		23-Mar		24-Mar				Mar 26 - 30

				Put lid on GG				Test DA Scripts										DA testing, stage mooring gear for cold test

		25-Mar		26-Mar		27-Mar		28-Mar		29-Mar		30-Mar		31-Mar				Apr 2 - 6

																		stage cold test, cold test, power budget

		1-Apr		2-Apr		3-Apr		4-Apr		5-Apr		6-Apr		7-Apr				Apr 9 - 13

										+/- DA, Load Reagents for thru dep + post QC		Pre-can QC, B, HAD, I, run with power monit/radio as with mooring, cold room mission written, start cold soak		Soak				deploy. Prep, ESP Shore ready,

		8-Apr		9-Apr		10-Apr		11-Apr		12-Apr		13-Apr		14-Apr				Apr 16 - 20

		Load FSW for negs, start remotely		(noon) Start pos		prep pucks, end cold test, thaw overnight		Load Pucks, can?		Can, postcan QC		Assemble mooring, prep for ship

		15-Apr		16-Apr		17-Apr		18-Apr		19-Apr		20-Apr		21-Apr

				Load on ship, deploy






