ESP Weekly Meeting 

15Mar07
Attending:

Doug Pargett, Scott Jensen, Chris Scholin, Cheri Everlove, Brent Roman





Next milestones: 
· Surface ESP, April 16 - May 7 (23 days, GG, Surface Mooring, CTD)

· Surface ESP, May 17 - June 12 (28 days, GG, Surface Mooring, CTD, ISUS)

· August XX (option):
D-ESP (DWSM, A1, Deep CTD, ISUS)
· Networked Surface ESP, Aug 30 – Sept 27 (GG, A1, 2 Moorings, ISUS, CTD)

Schedule:
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GG un-lid, Test 

tank new housing

19-Mar 20-Mar 21-Mar 22-Mar 23-Mar

Put lid on GG Test DA Scripts


1. Focus now to surface deployment
2. New housing, okay to cert to 20m by vacuum inside and test tank depth. It will be less time to use the GG lid. Will push for testing it over this weekend.

3. Chris thinks that the array bubbles could have been due to the permeability of helium into the reagents. We will do an N2 purge after the He leak test to <2 psi.

4. Manip. bug does not change the deployment plan. We know the signature error that is indicative of this fault. We are planning to spend a few days chasing this fault condition, on next Monday we’ll have a better decision.
5. DA test will run next Wednesday

6. Need to get the preparations for deployment knowledge out of Scott’s head and to others to help support future deployments. Will also capture the step-by-step for the manual that Dianne is writing.
7. GPS modem is being worked on. May include 4D’s in the box as well.
8. Possibility of new mooring design (Columbia River style) may be included in the 2008 year. Mid May time frame to meet with C-MOP about mooring. (CS)

9. Same deployment site and Shore coms.
10. Will want to have some hi-res exposures to this deployment. Science to decide what res images we’ll want.

11. Brent to add the ability to add/subtract hi-res images in the code.

12. Addie interview on 19th.  Presentation at 9:45am in Harbor.
13. Longer carousel for ESP, 132 pucks in current capacity. ASTEP goal is event response during deployment. Science will take what they can get. 
14. Engineering will keep in mind that there is the desire for more capacity, but no functional requirement as yet.
15. List of design reviews for 2007, will be sent to the ESP list.

16. The ASTEP DWSM housing will be the big, BIG, task for this year that we cannot do without. It may require a PCO action to get the engineering time and expertise that this task requires.

17. Scholin will put together an interest list for the workshop.
18. Update of A1: right at transition to testing sub-assemblies. We’ll need to make sure that A1 gets the new software. Brent to update.

19. Pucks, we will need the new pucks in house around August.
20. 1k DWSM bug testing will happen once Doug gets the springs here and installed. Probably about 2 weeks.
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		5-Mar		6-Mar		7-Mar		8-Mar		9-Mar						Mar 12 -16

																GG onto surface lid, Check Mooring Gear, Test DA

		12-Mar		13-Mar		14-Mar		15-Mar		16-Mar						Mar 19 - 23

										GG un-lid, Test tank new housing						Chris, Joe? Run new piezo arrays,

		19-Mar		20-Mar		21-Mar		22-Mar		23-Mar						Mar 26 - 30

		Put lid on GG				Test DA Scripts										DA testing, stage mooring gear for cold test

		26-Mar		27-Mar		28-Mar		29-Mar		30-Mar						Apr 2 - 6

																stage cold test, cold test, power budget

		2-Apr		3-Apr		4-Apr		5-Apr		6-Apr						Apr 9 - 13

																deploy. Prep, ESP Shore ready,

		9-Apr		10-Apr		11-Apr		12-Apr		13-Apr						Apr 16 - 20

		16-Apr		17-Apr		18-Apr		19-Apr		20-Apr






