ESP Weekly Meeting 

18Jan07
Attending:

Doug Pargett, Cheri Everlove, Scott Jensen, Roman Marin, Brent Roman, Gene Massion





Next milestones: 

GG Coldroom, Jan 22-24
DWSM Deployment, Feb 5, maybe Feb 12 as well
D-ESP Deployment, Mar 5-7 
GG Surface Deployment, Apr 16-May 7 (23 days)
GG Surface Deployment, May 17-June 12 (28 days)

Proposed Agenda:

· Switch to 2-2day D-ESP dives (Skip since Chris is out)

· Money, return of extra tech transfer parts (skip)

· Schedule for ‘07
· Devices to be developed/Integrated (ISUS, Deep CTD, MFB-PCR, 3k DWSM)

· DWSM status

· GG Status
· People Status

Proposed ’07 Schedule:
Feb 5:


DWSM

Feb 12:

?

March 5,6,7:

D-ESP (DWSM, GG, DEEP CTD)

April 16 - May 7:
Surface ESP (GG, Surface Mooring, CTD)

May 17 - June 12:
Surface ESP (GG, Surface Mooring, CTD)

June XX (option):
D-ESP (DWSM, A1, Deep CTD, ISUS)
Aug 30 – Sept 27:
Networked Surface ESP (GG, A1, 2 Moorings, MFB-PCR, ISUS)

Old Items

1. 3k ASTEP: Requirements definition: Haven’t come down to hard numbers yet. Scott, Chris, and Doug to start talking about requirements after the Dec 4 deployment. Put off until after the Jan 4th deployment. We can start now; I have 99% confidence that with the new valves (set and tested accordingly) DWSM will work great. Brent wants the DWSM system up and running for Ruby bug testing. It’ll be operationally back together this afternoon.


2. Testing of the new surface can is needed, Gene to develop the requirements. Doug to add it to the development schedule. Gene still to write up the reqmts. Gene will send the test reqmts to Doug Pargett.

3. We need to find a location to store these large parts. Cheri has made the requests for the space.


4. Jon will pull together solids and take a stab at an arrangement with his remaining time. Jon has sketched out an arrangement that will fit in the shallow water housing. We need to pick a surface deployment to incorporate the MFB-PCR into, and that is the networked deployment in late August.

5. Doug to request additional ‘07 days for people. Tried to do, but not getting anywhere yet. Will probably require a PCO action.

6. With the PCR unit looking like it will fit in the shallow water housing, the question for Chris is do we want to plan for a surface deployment with PCR? Scott thinks that lab and surface deployments will do very well at shaking the bugs out of a PCR module. 
7. Problem with the encoders. With an incredible stroke of luck, the encoders will be replaced.

8. The heater units for all 4 tech transfer machines were not made by El Camino. When one heater part was put on hold, El Camino put the entire order of heater assemblies on hold. We also need the brackets for the 3-way Burkert valve stacks for all 4 units. Mike Parker will be out until next Tuesday. We will need to get his input on the fastest way to get these parts. Heater parts for A1 made, brackets for A1 made, the remaining ones are planned to be made by El Camino.
NEW ITEMS


9. Do we have a way to track the instrument if it breaks free? We have the instrument but what do we need to do to integrate it?


10. Robust Core… Scott has 0 confidence that we can reliably do a back to back surface deployment in April-May. We need to keep a focus on a robust core.


11. Surface mooring options of multiple straps, Scott and Gene to discuss.

