ESP Weekly Meeting 

22Mar07
Attending:

Doug Pargett, Scott Jensen, Chris Scholin, Cheri Everlove, Brent Roman





Next milestones: 
· Surface ESP, April 16 - May 7 (23 days, GG, Surface Mooring, CTD)

· Surface ESP, May 17 - June 12 (28 days, GG, Surface Mooring, CTD, ISUS)

· August XX (option):
D-ESP (DWSM, A1, Deep CTD, ISUS)
· Networked Surface ESP, Aug 30 – Sept 27 (GG, A1, 2 Moorings, ISUS, CTD)

Schedule:
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Put lid on GG Test DA Scripts

26-Mar 27-Mar 28-Mar 29-Mar 30-Mar



Proposed Agenda:

Surface ops preparations

1. Readiness review 

2. Scott taking over the scheduling and planning for 
3. GG Robust core, sticky pucks, etc 
4. ISUS testing and mounting housings 
5. Battery decisions, etc 
ASTEP schedule for the year

1. Reviews 
2. Functional Requirements 
3. Additional engineering time (housing) 
4. Contingency plans…? 
5. Article 1 schedule 
Other

1. New hire status 

2. Micro Fluidic block status and mods 
3. Money ... 
Old Minutes:

1. Focus now to surface deployment
2. New housing passed proof test to 20m. New housing, okay to cert to 20m by vacuum inside and test tank depth. It will be less time to use the GG lid. Will push for testing it over this weekend.
3. Chris thinks that the array bubbles could have been due to the permeability of helium into the reagents. We will do an N2 purge after the He leak test to <2 psi.

4. Sticky puck and weak hand is the bug. We are looking at options. Manip. bug does not change the deployment plan. We know the signature error that is indicative of this fault. We are planning to spend a few days chasing this fault condition, on next Monday we’ll have a better decision.
5. DA test will run next Wednesday.
6. Need to get the preparations for deployment knowledge out of Scott’s head and to others to help support future deployments. Will also capture the step-by-step for the manual that Dianne is writing.
7. GPS modem is being worked on. May include 4D’s in the box as well.
8. Possibility of new mooring design (Columbia River style) may be included in the 2008 year. Mid May time frame to meet with C-MOP about mooring. (CS)

9. Same deployment site and Shore coms.
10. Will want to have some hi-res exposures to this deployment. Science to decide what res images we’ll want.

11. Brent to add the ability to add/subtract hi-res images in the code.

12. Longer carousel for ESP, 132 pucks in current capacity. ASTEP goal is event response during deployment. Science will take what they can get. Engineering will keep in mind that there is the desire for more capacity, but no functional requirement as yet.

13. The ASTEP DWSM housing will be the big, BIG, task for this year that we cannot do without. It may require a PCO action to get the engineering time and expertise that this task requires.

14. Scholin will put together an interest list for the workshop.
15. Update of A1: right at transition to testing sub-assemblies. We’ll need to make sure that A1 gets the new software. Brent to update.

16. Springs (several) are here, need to be installed. 1k DWSM bug testing will happen once Doug gets the springs here and installed. Probably about 2 weeks.
17. Pucks, we will need the new pucks in house around August.

New Minutes

18. DA test to run today and Piezo arrays
19. Need to calibrate the instrument heater for DA, no curve fit yet.

20. SH2 to also have a hold condition, 3 min or whatever doesn’t affect the lysate.
21. Jensen to take over the scheduling and planning of the surface deployments.
22. A RR will be needed to make sure we’ve got all the ducks (divers) lined up.

23. Need to complete the post crusies (Pargett to do)

24. Scott to cover the pre-cruise for the Surface ops.

25. Bob Herlien working on the pc laptop testing of our ISUS. The numbers to the ESP will be species calculated values. The log file is raw data. Increase in radio traffic is not bad, according to Brent. Bob to be charging ASTEP (703506.02)
26. ISUS testing needs a long serial cable for the test tank.
27. For deployment, would need a mount arrangement, serial cable, and tiem to include in the April deployment.

28. Pargett to follow up on the probe tips, and the options for surface vs deep.

29. Need to review what they were supposed to be delivering.

30. Scholin to find an account for new battery boxes.

31. No spare EM cable. Need to task building that up. Scott to take care of pinging Mark Brown for this task to Jim.

32. Description of the 4k DWSM schedule to get to the required strategic position at end of 2007.

33. Pushing the schedule is the only contingency condition we have.

34. New hire. Addie has till April 2 to accept. Looks good so far.

35. Micro-Fluidic Block 

36. LLNL has come thru with some specs for the IPC on PCR, some hints on Nucleic Acid purification column. 

37. Summer (science) student on C-More funds.

38. Scholin needs to write reports to Moore, etc., to demonstrate our progress. Start cutting PO’s on Moore for COTS parts. 
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		5-Mar		6-Mar		7-Mar		8-Mar		9-Mar						Mar 12 -16

																GG onto surface lid, Check Mooring Gear, Test DA

		12-Mar		13-Mar		14-Mar		15-Mar		16-Mar						Mar 19 - 23

										GG un-lid, Test tank new housing						Chris, Joe? Run new piezo arrays,

		19-Mar		20-Mar		21-Mar		22-Mar		23-Mar						Mar 26 - 30

		Put lid on GG				Test DA Scripts										DA testing, stage mooring gear for cold test

		26-Mar		27-Mar		28-Mar		29-Mar		30-Mar						Apr 2 - 6

																stage cold test, cold test, power budget

		2-Apr		3-Apr		4-Apr		5-Apr		6-Apr						Apr 9 - 13

																deploy. Prep, ESP Shore ready,

		9-Apr		10-Apr		11-Apr		12-Apr		13-Apr						Apr 16 - 20

		16-Apr		17-Apr		18-Apr		19-Apr		20-Apr






