ESP Weekly Meeting 

29Mar07
Attending:

Doug Pargett, Scott Jensen, Chris Scholin, Cheri Everlove, Brent Roman





Next milestones: 
· Surface ESP, April 16 - May 7 (23 days, GG, Surface Mooring, CTD)

· Surface ESP, May 17 - June 12 (28 days, GG, Surface Mooring, CTD, ISUS)

· August XX (option):
D-ESP (DWSM, A1, Deep CTD, ISUS)
· Networked Surface ESP, Aug 30 – Sept 27 (GG, A1, 2 Moorings, ISUS, CTD)

Schedule:
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Short meeting:
1. New manipulator bug is a broken wire. Being fixed right now.
2. Voltage limitation on the GPS modem makes it hard to power. We are looking into the remaining options.
3. Using existing battery boxes, oil filling for the alkalines. Jose has ordered the connection boards.
4. Check pointing and recovering and resuming seems to be very good so far.

5. 4kD functional requirements are coming soon. 

6. Back to DA right after the manip fix is completed.

7. User Scholin is the software to deploy. Neo to use user Brent code. (Brent’s sandbox.)

8. Cold room preps, mooring floats, radio, for cold room.

9. Load on Monday (April 16) morning. Pargett to bug Scott for the pre-cruise.

10. Need a better build cost of core plus mooring for WHOI. We can likely support two instrument deployment at same time in spring of ‘08 on east coast. Will need to be MBARI support for this. (Include in the ’08 proposals.)
11. Chris Scholin gone M-W of next week.
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		5-Mar		6-Mar		7-Mar		8-Mar		9-Mar						Mar 12 -16

																GG onto surface lid, Check Mooring Gear, Test DA

		12-Mar		13-Mar		14-Mar		15-Mar		16-Mar						Mar 19 - 23

										GG un-lid, Test tank new housing						Chris, Joe? Run new piezo arrays,

		19-Mar		20-Mar		21-Mar		22-Mar		23-Mar						Mar 26 - 30

		Put lid on GG				Test DA Scripts										DA testing, stage mooring gear for cold test

		26-Mar		27-Mar		28-Mar		29-Mar		30-Mar						Apr 2 - 6

																stage cold test, cold test, power budget

		2-Apr		3-Apr		4-Apr		5-Apr		6-Apr						Apr 9 - 13

		DA check		Prep, pre-dep runs, pre-can		Can, Cold soaking		Cold Runs		Cold Runs						deploy. Prep, ESP Shore ready,

		9-Apr		10-Apr		11-Apr		12-Apr		13-Apr						Apr 16 - 20

		Uncan, start load, mooring		mooring		prep		prep		Can for Dep

		16-Apr		17-Apr		18-Apr		19-Apr		20-Apr

		Load on ship, deploy






