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Task







Need
Expected
Ass’d

No.
Description





for
Due Date
To
1. Software

1.1. Basic Winch Functionality 



Zeph 
Cruise date


1.1.1. Using softline for the first Zephyr day



Gene
1.1.2. Const velocity mode w/level wind




Gene
1.1.3. monitor winch data and ESP data 



Gene


Note: accel and  pressure xducers may be mounted on the buoy
1.1.4. RS232 telemetry






Gene

 
Note: no network functionality or host controller on buoy
1.2. Intermediate functionality



W/F
Cruise date


1.2.1. Controlled tension mode





Gene

1.2.2. constant depth mode





Gene

1.2.3. network functionality





Wayne?
1.2.4. host controller on buoy





Brent?
1.2.5. basic system monitoring





Gene
1.2.6. error reporting






Gene
1.2.7. whatever else we learn we need 




Gene
1.3. Full Functionality




2010


Note: I’m not sure what additional functionality will be needed for Hawaii but I 
expect we’ll learn a lot from the cruises this year.

2. Mechanical

2.1. Winch

2.1.1. misc bits and pieces


Zeph
April 20
Mike

2.1.2. Buoy upper and lower frame

Zeph
April 20
Shop


Note: The shop assigned Mike to this

2.1.3. Electronics Enclosure


Zeph
May 7

Mike
2.1.4. Integration II




Zeph
April 30
Gene

Note: Integration I is going on now

3. Electrical

3.1. Interface electronics/cabling


W/F
May 15
Wayne

3.2. Freewave modem setup



Zeph
May 1

???

Note: I’d really like to get someone else on this task if possible

3.3. Host controller




W/F
May 15
Brent?
4. COTS Parts

4.1. Lebus core





Zeph
check’g now
Lebus

4.2. Surlyn buoy





Zeph
April 3

Gilman

4.3. Level wind motor




Zeph
April 5

CMC

4.4. Level wind gear head



Zeph
April 21
CMC

5. Testing

5.1. Bench testing





on-going
Gene
5.2. Wave simulator





April 15
Jim S.

5.3. Tank testing I




Zeph
May 5

Gene

5.4. Tank testing II




W/F
May 30
Gene
