Status April 6, 2017 – April 12, 2017 Two week Report

1. Travel/Out of office (if it’s changed)
 
2. Weekly Status (bullets or sentences)
901603 Video TAG:  

ToDo: Danelle is following up with Bluhaptics. Nancy is following up with UCSB. Duane is following up with Ocean Networks Canada and Univ Victoria. Duane is following up with Google. Duane is following up with SRI.

[bookmark: _GoBack]Visited with Mike Piacentino https://www.sri.com/about/people/michael-piacentino of SRI Monday April 10. Mike and his colleagues are under contract with NOAA to develop open source underwater video organism detection, tracking, classification using Deep Learning and other technologies. Through our NOAA AIASI activities Mike is looking into sharing his team’s development code with us. We have been sending that team image datasets to help move their work forward. They recently presented results, which are very encouraging, from MBARI rockfish habitat and other benthic ROV dives.

SRI is integrating their work into VIAME.  SRI is also making the code available stand-alone.

Ajmal Mian, our collaborator on the Australian Research Council project to apply machine vision to fish detection and measurement, who visited us last summer 2016, is exploring applying for a Fulbright Senior Scholarship to fund 3-4 month visit to US institution  (MBARI) to work with us on Deep Water Fauna Classification in Underwater Videos.  Applications close August 2017, and US visit period is between July 2018 and June 2019. Danelle and I think this would be terrific – Prof. Mian is a computer scientist with considerable experience and talent in the areas of interest to us.


901009 CANON:  
Updated Off Season 2017 STOQS database. Database is here:
http://stoqs.shore.mbari.org:8000/stoqs_os2017/query/ 


April 7 (Friday) is the official start of CANON Spring 2017. Brought up a new database to start collecting the data from assets in that campaign. (thanks Danelle) http://stoqs.shore.mbari.org:8000/stoqs_canon_april2017/query/ 

All current platforms are loaded and running, except slocum_nemesis, where we have an issue with the IOOS-standard aggregated netcdf files. I am going to try reading the individual netcdf files that Fred B. generates and sends to IOOS.

Dealt with issue of changes within netcdf files for L662 and G34. Made STOQS CANON April2017 available outside the firewall. Added nemesis, SG539 and SG621 to the STOQS load script. Resolved DODS/OPeNDAP issues with the DODS server for OA1, OA2 and wgTiny.

901618 Pelagic Benthic Coupling (Laser Measure): 
	Spinning up on Matlab. Focus is on user interface exploration (eg. how to select points in an image) and general capability. Dan has all of the core modules implemented in Matlab (reimplemented from Mathcad). Work now focuses on building a user-interface for the system, and starting discussion of integration of lasers in appropriate configuration onto the ROV(s).

901602 DataTAG: Nothing to report.

901023 Continental Margins: NTR

3. EC Worthy Notes: none

4. Other: Off the record: I am struggling with juggling CANON (now hectic with new platforms and annoying problems/changes), Laser Measure (where Dan is very focused and making very good progress) and VideoTAG (trying to keep collaborations moving forward, and trying to keep abreast of rapidly evolving capability in the community).
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