## Sheet1
Tasks | task sub section1 | task subsection2 | task subsection3 | time (Name, days) | cost
AHRS Down Selection
| ROS Driver review |  |  | Sebastian, 1
| Buy IMU only |  |  |  | 575
|  | Integrate drivers/device |  | Sebastian, 2
|  | Verify drift vs VectorNav |  | Sebastian, 1
| Select and procure IMU |  |  |  | 5000
| Select and procure antennas/cables |  |  | Bill, 1; George,1 | 300
Luxonis Testing
Buy
|  | OAK-FFC 4P PoE (used on mola) |  |  | 350
|  | 2x OAK-FFC AR0234 M12 |  |  | 200
|  | 2x OAK-FFC OV9282 M12 |  |  | 140
|  | 50cm flexes |  |  | 25
|  | Baseline Mounting kit |  |  | 30
|  | 45in rail |  |  | 60
Test/Integrate Algorithms on HW
|  | H265 encoding running on Luxonis HW |  | Eric, 3
|  | Perform a cal |  | George, 5
|  | RT depth map on Luxonis/Jetson |  | Eric, 10
|  | Test depth map accuracy at range to trade baseline, FOV, and # of arrays |  | George, 5
|  |  | buy laser distance meter |  | 400
| Finalize Vision System Trade (#modules, system FoV and range, lenses, mounting locations, baseline) |  |  | George, 5; Bill, 6
| Data compression with real scenes |  |  | George, 1
Optics downselection
|  | Buy lenses/filter candidates |  |  | 200
|  | Optics integration |  | George, 2
| Design/Build 1st Paragon vision sensor |  |  | Bill, 5; George 2
| Test 1st Vision sensor on Paragon |  |  | George, 2
Paragon Control
Buy
|  | 2x Yamaha Analog Gauge Interface (6Y9-8A2D0-30-00) |  |  | 300
|  | Arduino or similar and configure to spew ADC counts over USB UART |  | Eric, 1 | 20
| Integrate module (electrically) on the Paragon |  |  | George, 3
Test Lidar range |  |  |  | George, 3
Test AHRS
| noise/bias |  |  | George 2, Sebastian 2
| Accuracy using ship/ROV truthsource (and build test fixture) |  |  | George 1, Sebastian 2, Bill 2 | 100
Assemble Remaining Vision Sensors
| Buy material (modules or CCMs, interconnect, Optics, housing/mounting |  |  |  | 3500
| Assemble |  |  | Bill, 2; George, 2
| Integrate/Test |  |  | George, 1
Design and Order Networking and Power
| Buy material (power supplies, cables, enclosures, mounting) |  |  |  | 2500
| Buy managed Switch |  |  |  | 2000
| 8tb solid state M2key |  |  |  | 2000
| System design |  |  | George, 4; Bill 4
Mount systems on Paragon
| Design/Build lidar mounting |  |  | Bill, 3 | 250
| Design/Build AHRS mounting |  |  | Bill, 3 | 250
| Assemble systems on Paragon |  |  | Bill, 5 George, 4
Wind Sensor |  |  |  |  | 1300
|  |  |  | Total | 19500