MARS Status August 18, 2009
Current Experiments

1. MOBB on port 1
2. Sensor Group on port 4

3. EK60 on port 6 thru 9/2009
4. EITS on port 8
Issues

Interface cables/ODI connectors
Craig sent a message requesting current status/expected delivery dates on all cables from ODI.
High voltage safety
Safety procedures in process.
Initial Cable order Usage

Ventana Interconnect
 – MNK 10L/MNK 10L - 4 Meters @ Seacon
ESP – ODI 12 way/ MNK 10L – 70 Meters @ Seacon
WHOI – 70 Meters – Shipped 7/22/2009
Chadwick – 70 Meters

MARS PTT – ODI 12 way/MNK 10L – 5 Meters @ Seacon
UCSD - 80 Meters – Shipped 7/9/2009
All of cable allocated.  Chadwick 70 meters still on hand.
Port Adapter Cable Assembly

PO submitted.  12 week lead time but 2 weeks is MBARI drawing approval.  Awaiting for drawing for approval.
EK60

UW measured acceptable noise levels after EITS was deployed.  Currently powered on.
WNS PC104 stack issues
WNS is functional but still have temporary power supply and limited status on port power.  Needed for both the FOCE and EK60 this month.
Bury MOBB Cable
NFS raised issue of burying MOBB cable.  Permitting issue?

CISCO security changes
Pete needs the changes reviewed and then the go ahead to 

install them.  Question for Pete, do you want to first install on the WNS or go directly onto MARS?  Installed on WNS but not the MARS node itself.
MV Converter
Awaiting more information from Keith.  Power data was successfully gotten 8/14/2009.
Web Site Review Meeting
Everyone should have received an email pointing to a first pass proposal on new web page.
Schedule MARS Power Down for Service
Looking to do in the October timeframe.
Habitat and Biological Impact survey
To be conducted in the January through April 2010 time frame.  Survey of the MARS cable to evaluate impact.  Jim Barry and Linda Kuhnz.  Will require multiple dive days.
Acoustic Communications Base Station for MARS
It has been discovered this is to include a float 50 meters above the base instrument.  Issue is entanglement with ROV tether.
Future deployments

Rover
Rover is looking for a boat day to deploy onto MARS in the October/November timeframe.

FOCE

August 31, 2009

Connect to port 2

Acoustic Communications Base Station for MARS
10/28/2009
Lee Freitag @WHOI
BPR/Tilt instrument for MARS
11/4/2009
Bill Chadwick @NOAA

Scott Stalin @NOAA/PMEL

ESP
10/1/2009 thru 10/26/2009
11/25/2009 til early 2010

Chris Scholin
OBS Seismometer

December 2009 for 6 months

John Orcutt

Large Aperture Array

2011
NPS

Chinese MARS Node

Dejun Li @Zhejiang University, China

Further details unknown
No further communications

In-situ calibrator for ph measurement
Kang @Dept of Geology and Geophysics, Univ of Minnesota
Proposed MARS layout
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