MARS Status March 9, 2010
Current Experiments - 3
· ACOMMS on port 3
· EK60 on port 6
· EITS on port 8
Issues
MARS Port 4 Connector Pin 12 Failure

Port 4 is being planned to be used for PHOBOS.
MOBB Move to Port 5

MOBB will be moved from port 1 to the docking station under port 5.
Ricketts Ability to Service MARS

Need to look at Ventana tools developed for MARS access.  
MVC Testing

We are now about 1.5 weeks away from testing the new MVC.
EITS Pan and Tilt Problem
EITS’ P&T is causing problems.  The ROV fly by on 2/17/2010 showed some fizzing on the P&T but all connectors looked good.
MARS Lab UPS
The MARS lab UPS is marginally powered.  The new UPS has been received.  Need to schedule change over when time permits.  Probably be done when new servers are installed.
EOI Door Sensor

The contractor installed and wired most of the hardware necessary for monitoring the door switch at the end of the island.  He had to take some of the cards back for programming.  More time will need to be scheduled to finish the job.
Future deployments/recoveries
MARS Cable Survey

Started 1/8/2010
ACOMMS
Recover 8/23/2010
Port 3
Lee Freitag @WHOI
FOCE

Deploy 3/22/2010 Delayed
Recover August 22nd - ?
Will attach to port 2

LOOKING (was OBS Seismometer)

Deploy 3/26/2010
Recover 9/30/2010
Will attach to port 1
John Orcutt @UCSD

EITS

Recover 3/24/2010

BPR/Tilt instrument for MARS
Deploy 6/30/2010
Recover 12/14/2010
Will attach to port 7

Bill Chadwick @NOAA

Scott Stalin @NOAA/PMEL

ESP

Deploy 11/30/2010

Recover – Not known yet

Will attach to port ?

Large Aperture Array

2011
NPS

Chinese MARS Node

Dejun Li @Zhejiang University, China

Application is in to NSF.  Plan to be on MARS for 3 months.
SAIC – Naval Hydrodynamics Division
Have expressed an interest in connecting to MARS from November 2010 until February 2011.
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