MARS Status January 19, 2011
Current Experiments – 3
· LOOKING on port 1

· PHOBOS on port 4

· BPR/Tilt on port 7

Issues
ESP Shutdown
ESP testing  on the WNS ended 1/18/2011.  (12 days – no problems)
PG&E Power Failure 1/2/2011

A power failure resulted in a shutdown of MARS.  The length of the failure exceeded the UPS capacity at the end of the island.  It appears the UPS held MARS up for approximately 1 hour.

Tongji University, China
 Awaiting permit from Sanctuary (rest in place).  Craig is visiting this week.  Want to be here 1st of March for testing on WNS.
MARS West Gb Link is Down

The link is still down but the East link is running without errors.  Debug efforts will be scheduled again soon.
MARS EOI Maintenance

Several items need to be addressed at the EOI:

1. Sea water ground check

2. Power supply maintenance

3. UPS service

EOI Door Sensor

Still waiting for install to be re-scheduled
MOBB 
The deployment of new cable is April 6 & 7 on the Western Flyer.  Dates are questionable.
Sediment Events Sensor

Testing in April, deployment in May.  Bottom mount only.  Cable length unknown.  Need questionnaire filled out.  Permitting okay.

ROV Trenching Tool

Testing of the ROV trenching tool to lay a cable went well but need to add tensioning indicator.
Port Test Tool (PTT)

The PTT is being redesigned to enhance its current capabilities and add some new ones.  Changes are being driven by experience working with MARS.  Targeting February 2011 for WNS testing.
Neptune web write up on MARS

Monterey Accelerated Research System (USA)

The Monterey Accelerated Research System (MARS) is a cabled ocean observatory planned for installation on the seafloor in Monterey Canyon off the California coast. The MARS science node will be installed on the seafloor at a depth of 891 meters (2,923 feet), on a broad, muddy platform called Smooth Ridge. MARS is an initiative of the Monterey Bay Aquarium Research Institute (MBARI).
Kim is going to re-write it.
CISCOs

Pete to roll the new CISCO security scripts out to the node on 1/25/2011.

ONR

Large Aperture Array

NPS - 2012 maybe

Future deployments/recoveries
FOCE

Deploy 4/4/2011
Recover 10/13/2011
Port 2

LOOKING
Recover June 29, 2011
Port 1

John Orcutt @UCSD

BPR/Tilt instrument for MARS
Recover June 28, 2011
Port 7

Bill Chadwick @NOAA

Scott Stalin @NOAA/PMEL

Ghost Buster
Deploy 9/29/2011

Recover 11/30/2011
Port 8 7?
Funding not yet established.
Kang Ding – University of Minnesota
MOBB

Lay new cable 4/6/2011 & 4/7/2011
Tongji MARS Node

Deploy 3/14/2011
Recover 4/20/2011
Port 6
Dr.  Huaiyang Zhou @Tongji University, China

Sediment Events Sensor

Deploy 5/19/2011 ?
Recover 11/22/2011 ?
Port 8?
Ken Smith
ONR

Deploy 6/20/2011
Recover 12/15/2011

Port 3

Clare Reimers – Oregon State

MARS O&M Days

11/28/2011, 11/29/2011
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