MARS Status July 12, 2011
Current Experiments – 6
· LOOKING on port 1

· FOCE on port 2

· PHOBOS on port 4

· MOBB on port 5

· Tongji on port 6

· BPR/Tilt on port 7

Issues
LOOKING

Looking is now extended until October.
BMFC
Will need to use port 4 (PHOBOS’ port).  Deploying in September for 6 months but still show boat day in December.
Sediment Events Sensor

Deployment has slid out for August 11.  Working with Paul to define network and schedule testing.
PHOBUS

New tripod mounted light shorted out.  Apparent sea water leak.  Caused major 375 common ground fault that could not be isolated.
MARS Dead Face Relays

PHOBOS failure showed up a failed dead face relay failure.  Still working to understand.  May be a relay issue.

Port Test Tool (PTT)

The PTT is being redesigned to enhance its current capabilities and add some new ones.  Changes are being driven by experience working with MARS.  Will add ability to test dead face relays.
MARS Data Into SSDS

Rich has completed most of his work.  Now needs to do the verification phase.  Actual entry of data into SSDS might take a bit longer (up to several months).  
MARS EOI Maintenance

Several items need to be addressed at the EOI:

1. Sea water ground check

2. Power supply maintenance

3. UPS service

MARS West Gb Link is Down

The link is still down but the East link is running without errors.  Debug efforts will be scheduled again soon.

EOI Door Sensor

Still waiting for install to be re-scheduled
Future deployments/recoveries
Sediment Events Sensor

Deploy 8/11/2011
Recover 10/25/2011
Port 3
Ken Smith

BMFC

Deploy 9/20/2011

Recover 6 months later – Issue!
Port 1

Ghost Buster
Deploy 9/29/2011

Recover 11/30/2011
Port 8

Funding not yet established.
Kang Ding – University of Minnesota
LOOKING
Recover October 2011

Port 1

John Orcutt @UCSD

Tongji University
Recover 10/26/2011 & 10/27/2011

Port 6
Dr.  Huaiyang Zhou @Tongji University, China

ESP

Deploy April 2012 - Issue
Recover 6 months later
Port 3

MARS O&M Days

11/28/2011, 11/29/2011
FOCE

Recover May 2012 - Issue
Port 2

BPR/Tilt instrument for MARS
Recover June 2012
Port 7

Bill Chadwick @NOAA

Scott Stalin @NOAA/PMEL
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