MARS Status June 14, 2011
Current Experiments – 5
· LOOKING on port 1

· FOCE on port 2

· PHOBOS on port 4

· Tongji on port 6

· BPR/Tilt on port 7

Issues
LOOKING

LOOKING has been extended to at least the end of August.  If it goes longer, BMFC will have to use PHOBOS’ port.  Need to swap out the current cable adapter.
FOCE

CO2 fill planned for 6/20 & 21.  CO2 fill may be bumped by a need to repair FOCE fan.
BPR

Have PO, BPR is extended thru June 2012.
BMFC
Use to be called ONR.  Stands for Benthic Microbial Fuel Cell.  Want to deploy in September for 6 months.
Tongji University, China
Network on control computer appears to have stabilized.
MOBB 
Deployment date 6/22/2011 & 6/23/2011.  It will be done on the WF.  Documented network setup, Pete has implemented.  Need to work detailed cable lay plan to avoid Tongji.
ROV Trenching Tool

LOBOS test will be done with the modified cable laying sled June 16.  Cable lay will take place June 22 and 23.
Sediment Events Sensor

Deployment has slid out for August 11.  Working with Paul to define network and schedule testing.
PHOBUS

Planning deployment of a new light that will be on a tripod.  Will not be able to re-aim.
MARS OBC is Up

OBC hardware ¾ functional.  DCS server serial port now works.  1PPS is being tested.  Testing is still ongoing.  An issue was seen with a major increase in jitter.  Still investigating but it has been working fine for a little over a week.

Port Test Tool (PTT)

The PTT is being redesigned to enhance its current capabilities and add some new ones.  Changes are being driven by experience working with MARS.  
MARS Data Into SSDS

Rich has completed most of his work.  Now needs to do the verification phase.  Actual entry of data into SSDS might take a bit longer (up to several months).  
MARS EOI Maintenance

Several items need to be addressed at the EOI:

1. Sea water ground check

2. Power supply maintenance

3. UPS service

MARS West Gb Link is Down

The link is still down but the East link is running without errors.  Debug efforts will be scheduled again soon.

EOI Door Sensor

Still waiting for install to be re-scheduled
Future deployments/recoveries
MOBB

Cable lay date is 6/22/2011 & 6/23/2011.

Sediment Events Sensor

Deploy 8/11/2011
Recover 10/25/2011
Port 3
Ken Smith

LOOKING
Recover End of August 2011 (Maybe)
Port 1

John Orcutt @UCSD

BMFC

Deploy 9/20/2011

Recover 6 months later

Port 1

Ghost Buster
Deploy 9/29/2011

Recover 11/30/2011
Port 8

Funding not yet established.
Kang Ding – University of Minnesota
Tongji University
Recover 10/26/2011 & 10/27/2011

Port 6
Dr.  Huaiyang Zhou @Tongji University, China

ESP

Deploy April 2012
Recover 6 months later
Port 3

MARS O&M Days

11/28/2011, 11/29/2011
FOCE

Recover May 2012
Port 2

BPR/Tilt instrument for MARS
Recover June 2012
Port 7

Bill Chadwick @NOAA

Scott Stalin @NOAA/PMEL
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