MARS Status June 28, 2011
Current Experiments – 5
· LOOKING on port 1

· FOCE on port 2

· PHOBOS on port 4

· Tongji on port 6

· BPR/Tilt on port 7

Issues
LOOKING

Looking is now extended until October.  The 1 PPS adapter was successfully swapped last week.
FOCE

Foce did a partial CO2 fill and spent the second day getting both fans fixed.
BMFC
Use to be called ONR.  Stands for Benthic Microbial Fuel Cell.  Want to deploy in September for 6 months.  Will need to use port 4 (PHOBOS’ port)
MOBB 
Deployed and working well.  Despite some issues, cable burial went well.
Sediment Events Sensor

Deployment has slid out for August 11.  Working with Paul to define network and schedule testing.
PHOBUS

Deployed  a new light on a tripod.  This is a major improvement in image quality.  Will be recovering PHOBOS for maintenance in the fall.
Port Test Tool (PTT)

The PTT is being redesigned to enhance its current capabilities and add some new ones.  Changes are being driven by experience working with MARS.  
MARS Data Into SSDS

Rich has completed most of his work.  Now needs to do the verification phase.  Actual entry of data into SSDS might take a bit longer (up to several months).  
MARS EOI Maintenance

Several items need to be addressed at the EOI:

1. Sea water ground check

2. Power supply maintenance

3. UPS service

MARS West Gb Link is Down

The link is still down but the East link is running without errors.  Debug efforts will be scheduled again soon.

EOI Door Sensor

Still waiting for install to be re-scheduled
Future deployments/recoveries
Sediment Events Sensor

Deploy 8/11/2011
Recover 10/25/2011
Port 3
Ken Smith

BMFC

Deploy 9/20/2011

Recover 6 months later

Port 1

Ghost Buster
Deploy 9/29/2011

Recover 11/30/2011
Port 8

Funding not yet established.
Kang Ding – University of Minnesota
LOOKING
Recover October 2011

Port 1

John Orcutt @UCSD

Tongji University
Recover 10/26/2011 & 10/27/2011

Port 6
Dr.  Huaiyang Zhou @Tongji University, China

ESP

Deploy April 2012
Recover 6 months later
Port 3

MARS O&M Days

11/28/2011, 11/29/2011
FOCE

Recover May 2012
Port 2

BPR/Tilt instrument for MARS
Recover June 2012
Port 7

Bill Chadwick @NOAA

Scott Stalin @NOAA/PMEL
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