MARS Status May 3, 2011
Current Experiments – 4
· LOOKING on port 1

· PHOBOS on port 4

· Tongji on port 6

· BPR/Tilt on port 7

Issues
ONR

Back to life.  Deployment in the fall for maybe 6 moths.  Need details!
Tongji University, China
Working well.  Next step is movement of computers to MARS’ lab.  Will require some additional set up.
MARS West Gb Link is Down

The link is still down but the East link is running without errors.  Debug efforts will be scheduled again soon.
MARS OBC is Down

OBC hardware ¾ functional.  Working at getting server serial ports going.
MARS EOI Maintenance

Several items need to be addressed at the EOI:

1. Sea water ground check

2. Power supply maintenance

3. UPS service

EOI Door Sensor

Still waiting for install to be re-scheduled
MOBB 
Deployment date unknown.  It will be done on the WF.  Need to document (verify) network setup.  Need to work detailed cable lay plan to avoid Tongji.
ROV Trenching Tool

ROV trenching tool worked well but need to add tensioning indicator.  Need to move to DR tool sled.
Sediment Events Sensor

Deployment is scheduled but nothing else.  Need to confirm cable length.
Port Test Tool (PTT)

The PTT is being redesigned to enhance its current capabilities and add some new ones.  Changes are being driven by experience working with MARS.  
Neptune web write up on MARS 

Neptune and Wikipedia corrected.
MARS Data Into SSDS

Rich has completed most of his work.  Now needs to do the verification phase.  Actual entry of data into SSDS might take a bit longer (up to several months).  As it turns out, MARS is the guinea pig for the new SSDS ingest system.
MARS Scheduling

MARS is highly populated for the second half of the year.  Any changes or any thing new will be even more of a balancing act.

Future deployments/recoveries
FOCE

Deploy 5/4/2011
Recover 10/13/2011 (could be extended into 2012)
Port 2

Tongji Test
Deploy 4/20/2011 & 4/21/2011
Recover 10/26/2011 $ 10/27/2011
Port 6
Dr.  Huaiyang Zhou @Tongji University, China

Sediment Events Sensor

Deploy 6/30/2011
Recover 10/25/2011
Port 3
Ken Smith

BPR/Tilt instrument for MARS
Recover 2012
Port 7

Bill Chadwick @NOAA

Scott Stalin @NOAA/PMEL

LOOKING
Recover June 29, 2011

Port 1

John Orcutt @UCSD

Ghost Buster
Deploy 9/29/2011

Recover 11/30/2011
Port 8

Funding not yet established.
Kang Ding – University of Minnesota
ESP

Deploy 11/10/2011

Recover 2012
Port 3

MOBB

Cable lay date is 6/22/2011 & 6/23/2011.
MARS O&M Days

11/28/2011, 11/29/2011
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