MBARI MARS

Army Corps of Engineers Permit Application Needs
1. Block 24:  Names and full mailing addresses of adjoining property owners, lessees etc, whose property adjoins the waterbody or aquatic site where the work is being proposed.

See blue highlights on attached spreadsheet. Also see apn_maps.pdf. 
2. Figure 5 in permit:  Please update the planned HDD layout to include any trenching (as we discussed in our meeting) no matter how short all dimensions of buildings, concrete slabs, etc.  I have some of this information on another graphic (not the trench), but it might be helpful to have all on one graphic for expedited agency review.  We can discuss.

The architects should have a drawing available on Wednesday, 5/18.
3. Figure 7 (new):  Confirm attached figure is the most current and correct route for the on-shore cable.

Yes, this is the most current figure.

4. Confirm:  Will the Proposed Landing Area Route be replaced by the Alternative 2 Landing Area (MLML Pier) per the Monterey County comment letter dated April 21, 2005?

There are serious concerns about cable survivability with this option, so we will not be changing this to the preferred route.

5. Let’s discuss strategy for getting the confidential Cultural Report to the agencies that need it.  It IS part of the Application package.  I have some ideas we can talk about.

Jon Davidson from Aspen has sent a copy of this report to the CCC and ACOE in the requested format. (See Jon’s email dated 5/17/05).

6. Provide new figure for cover the ACOE Draft Permit cover is outdated – or we can create one on our own…lets discuss.

Attached.

California Coastal Commission Permit Application Needs

1. Confirm fishing agreement is in place or provide projected date of final agreement.

The fishing agreement has not been finalized yet. I will call you to discuss details.

2. Provide information in as much detail as possible about how often the cable will be surveyed, and what portions will be surveyed.  There is a brief discussion in the EIS, but lets talk about what other (more specific) information we can provide for the agencies – if any.

The cable will be surveyed 2 years after deployment and thereafter, every 5 years.  We will only survey the cable in the highest risk areas, near the HDD entrance pipe near shore, the unburied section on the neck of Smooth Ridge and near the node.  We will also survey a few locations on the shelf.  If the cable were found to be unburied in sections that where previously buried, we would rebury the cable if there were a serious risk to cable damage if left unburied.  We would not rebury the cable if it were unburied in a designated no trawl zone on the shelf. Our geologists have indicated that we are in a period of sediment build up on the shelf, so it is unlikely that the cable will become unburied over its lifetime. 

3. Confirm that HDD activities or any other project activities will not interfere with coastal access or beach area near the landing site. 

HDD operations will be set up behind fencing on MBARI property. Therefore, access to the beach will not be affected.  

4. What is the projected total cost of development for the project?

Alison Dettmer indicated that we would only need to include physical development costs out to the State jurisdiction (3-mile mark).

Here is the best estimate:

HDD: $600k

Shore side modular building, electrical and civil work: $90k

Cable lay 3mls (cable ship $65k/day, cable laid at 0.5kt (6hrs) + shore side work: $65k

Total: $755k

5. Please confirm which is the most current/accurate geology and soils report: BAS/Fugro, USGS 1995 Samples, or Rutherford 2004. Or other?

BAS/Fugro and November 2004 report written by geologist Charlie Paull. (See my email to you dated 5/10/05.)

6. What is the height and width of the ISO van proposed for the site (length is 20 feet)? What is the ISO van’s elevation from ground once installed (assuming 2-4 feet??)?

We are no longer planning to use an ISO van. We will be putting up a modular-type building of the same rough dimensions as an ISO van. Should have drawings by Wednesday, 5/18.

7. Size of the entire parcel (133-252-001) in sq ft.

Parcel is 3.03 acres (131,970 sq. ft.).
8. Is grading proposed for the concrete pad that supports the ISO van – if so how much (cubic ft).  Is grading required for concrete pad supporting the HDD rig – if so, how much (cu ft).  What about fill? Will any fill be used- how much (cubic ft.).

Should know by Wednesday, 5/18.

9. Are extensions of the electric utilities proposed? If so, above ground/underground?  EIS says power would be supplied from existing overhead electrical distribution line (page 2-15) – any extension or up grades needed?

A new transformer and power pole are already going to be installed (in the next couple of months). But these would have been installed independent of MARS. A contractor will be installing the pole. PG & E will be running the wire from the previous pole to the new pole and placing the new transformer in. A step-down transformer and pad will be done by a contractor.
10. Height of chain link fence surrounding gravel storage yard.  Area (sq. ft.) enclosed.  What is the location of the fenced storage yard within the MBARI parcel? (Middle? Southeast corner? Along western boundary?) 

The fence is approximately 8 feet high. I have attached a drawing showing the location of the fence with dimensions.
11. Provide proof of applicant’s legal interest in property (current tax bill, recorded deed, lease, easement, or current insurance policy).

See attached.

12. Names and addresses of property owner and occupant of property situated within 100 feet of property lines of MBARI parcel.

See spreadsheet attached.

13. List of names and addresses of all parties known to the applicant to be interested in the proposed project (names of those who attended the public scoping and draft EIS/EIR public comment meetings, any others?)

See spreadsheet attached. This is a list of non-agency and non-consulting people who attended either of the public meetings or requested a copy of the draft document. I can try to come up with more if you think it’s necessary. This is all that came to mind.
